## SAP BP
Line of Business | Business Area | Country/Region Key | Scope ID | Scope ID Description | Complexity | Wokshops & Configuration | Unit Testing | Integration Testing | Documentation, Training core User | User Acceptance Testing | Total | Comments
Application Platform and Infrastructure | Process Management and Integration | US | 1NN | Business Event Handling | Best Practice
Application Platform and Infrastructure | Process Management and Integration | US | 1NJ | Responsibility Management | Best Practice
Application Platform and Infrastructure | Process Management and Integration | US | 31N | Situation Handling | Best Practice
Asset Management | Maintenance Management | US | BH1 | Corrective Maintenance (successor: 4HH) | Best Practice | 2 | 4 | 4 | 2 | 2 | 12
Asset Management | Maintenance Management | US | BH2 | Emergency Maintenance (successor: 4HH) | Best Practice | 2 | 3 | 3 | 3 | 1 | 11
Asset Management | Maintenance Management | US | 43R | Maintenance Resource Scheduling | Best Practice | 4 | 5 | 5 | 3 | 2 | 17
Asset Management | Maintenance Management | US | BJ2 | Preventive Maintenance (successor: 4HI) | Best Practice | 4 | 5 | 5 | 3 | 2 | 17
Asset Management | Maintenance Management | US | 4HI | Proactive Maintenance | Best Practice | 4 | 5 | 5 | 3 | 2 | 17
Asset Management | Maintenance Management | US | 4HH | Reactive Maintenance | Best Practice | 4 | 5 | 5 | 3 | 2 | 17
Database and Data Management | Enterprise Information Management | US | 2Q2 | Data Migration to SAP S/4HANA from Staging | Best Practice
Database and Data Management | Enterprise Information Management | US | 1I9 | Master Data Catalog for SAP S/4HANA - On-premise | Best Practice
Finance | Accounting and Financial Close | US | J58 | Accounting and Financial Close | Best Practice | 15 | 5 | 2 | 6 | 2 | 30 | Enterprise setup, COA Finalization, Reporting structures, approvals, Period endclosing
Finance | Accounting and Financial Close | US | 1GA | Accounting and Financial Close - Group Ledger IFRS | Best Practice | 3 | 2 | 1 | 2 | 0.5 | 8.5
Finance | Accounting and Financial Close | US | 2FD | Accounting for Incoming Sales Orders | Best Practice | 6 | 2 | 3 | 2 | 1 | 14 | Predictive accounting, extension ledgers
Finance | Accounting and Financial Close | US | 33Q | Actual Costing | Best Practice | 15 | 5 | 5 | 3 | 2 | 30 | Efforts depends on no.of plants and plant specific requirements
Finance | Accounting and Financial Close | US | J62 | Asset Accounting | Best Practice | 10 | 5 | 3 | 3 | 1 | 22
Finance | Accounting and Financial Close | US | 1GB | Asset Accounting - Group Ledger IFRS | Best Practice | 3 | 2 | 1 | 2 | 0.5 | 8.5
Finance | Accounting and Financial Close | US | 6DS | Asset Accounting - Group Ledger IFRS (UPA) | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 6DR | Asset Accounting (UPA) | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | BFH | Asset Under Construction | Best Practice | 4 | 2 | 2 | 2 | 0.5 | 10.5
Finance | Accounting and Financial Close | US | 1GF | Asset Under Construction - Group Ledger IFRS | Best Practice | 2 | 2 | 1 | 2 | 0.5 | 7.5
Finance | Accounting and Financial Close | US | 6DU | Asset under Construction - Group Ledger IFRS (UPA) | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 6DT | Asset under Construction (UPA) | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 1GO | Cash Journal | Best Practice | 2 | 1 |  | 2 | 0.5 | 5.5
Finance | Accounting and Financial Close | US | 1J2 | Compliance Formats - Support Preparation | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 1K2 | Event-Based Revenue Recognition - Sell from Stock | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 33M | Event-Based Revenue Recognition - Sell from Stock - IFRS | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 3M3 | Event-Based Revenue Recognition - Service Documents | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 3M4 | Event-Based Revenue Recognition - Service Documents - IFRS | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 6AK | Event-Based Revenue Recognition - Service with Adv. Execution | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 6AL | Event-Based Revenue Recognition - Service with Adv. Execution - IFRS | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 2OO | External Tax Audit | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 2FM | Financial Planning and Analysis | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 3SS | General Indirect Tax in the Canary Islands | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 1GI | General Ledger Allocation Cycle | Best Practice | 5 | 2 |  | 1 | 1 | 9
Finance | Accounting and Financial Close | US | 4RC | Integrated Financial Planning | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 4LG | Intelligent Intercompany Reconciliation | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 40Y | Intercompany Reconciliation Process | Best Practice | 20 | 5 | 5 | 5 | 5 | 40 | ICMR for Local & Group level Intercompany transactions matching
Finance | Accounting and Financial Close | US | BEJ | Inventory Valuation for Year-End Closing | Best Practice | 4 | 2 |  | 1 | 1 | 8
Finance | Accounting and Financial Close | US | 1ZT | Managing Material Price Changes and Inventory Values | Best Practice | 2 | 1 | 1 | 1 | 1 | 6
Finance | Accounting and Financial Close | US | 2V7 | Monitoring of Goods and Invoice Receipts | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 4PG | Organizational Flexibility in Financial Accounting | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | BF7 | Period-End Closing - Maintenance Orders | Best Practice | 3 | 2 | 1 | 1 | 1 | 8
Finance | Accounting and Financial Close | US | BEI | Period-End Closing - Plant | Best Practice | 8 | 5 | 2 | 3 | 2 | 20
Finance | Accounting and Financial Close | US | 2VB | Purchase Order Accruals | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 5VW | Revenue Accounting | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 2QY | SAP Fiori Analytical Apps for Asset Accounting in Finance | Best Practice | 1 | 2 |  | 1 | 1 | 5
Finance | Accounting and Financial Close | US | BGC | SAP Fiori Analytical Apps for G/L Accounting in Finance | Best Practice | 1 | 2 |  | 1 | 1 | 5
Finance | Accounting and Financial Close | US | 63L | Service Entry Sheet Based Accruals | Best Practice | [5 empty] | 0
Finance | Accounting and Financial Close | US | 6DF | Universal Parallel Accounting | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 5XU | Document and Reporting Compliance | Best Practice | 15 | 10 | 10 | 5 | 5 | 45
Finance | Advanced Accounting and Financial Close | US | 3AF | Group Account Preparation for Financial Consolidation | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 5PU | Group Financial Planning | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 4VB | Group Reporting - Consolidation with Multiple Group Currencies | Best Practice | 2 | 1 | 1 | 1 | 1 | 6
Finance | Advanced Accounting and Financial Close | US | 2U6 | Group Reporting - Data from External Systems | Best Practice | 5 | 2 | 2 | 2 | 2 | 13
Finance | Advanced Accounting and Financial Close | US | 287 | Group Reporting - Data from SAP Group Reporting Data Collection | Best Practice | 20 | 5 | 5 | 5 | 5 | 40
Finance | Advanced Accounting and Financial Close | US | 4R7 | Group Reporting - Environmental, Social, and Governance Data | Best Practice | 5 | 1 | 1 | 1 | 1 | 9
Finance | Advanced Accounting and Financial Close | US | 1SG | Group Reporting - Financial Consolidation | Best Practice | 40 | 10 | 10 | 10 | 10 | 80 | Group reporting Legal consolidation & Without concidering any custom functionalities
Finance | Advanced Accounting and Financial Close | US | 3LX | Group Reporting - Matrix Consolidation | Best Practice | 10 | 3 | 3 | 3 | 3 | 22
Finance | Advanced Accounting and Financial Close | US | 28B | Group Reporting - Plan Consolidation | Best Practice | 10 | 3 | 3 | 3 | 3 | 22
Finance | Advanced Accounting and Financial Close | US | 3F7 | Joint Venture Accounting | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 1T6 | Lease-In Accounting | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 21P | Lease-In Accounting - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 6EC | Lease-In Accounting - Group Ledger IFRS (UPA) | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 6EB | Lease-In Accounting (UPA) | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 21Q | Lease-Out Accounting | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 2SB | Lease-Out for Sublease Accounting | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 2SA | Lease-Out for Sublease Accounting - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 6EE | Lease-Out for Sublease Accounting - Group Ledger IFRS (UPA) | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 6ED | Lease-Out for Sublease Accounting (UPA) | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 3F4 | Sales-Based Rent | Best Practice | [5 empty] | 0
Finance | Advanced Accounting and Financial Close | US | 21R | Service Contract | Best Practice | [5 empty] | 0
Finance | Advanced Financial Operations | US | 1QM | Advanced Credit Management | Best Practice | 40 | 5 | 10 | 3 | 2 | 60
Finance | Advanced Financial Operations | US | BD6 | Basic Credit Management | Best Practice | 15 | 5 | 5 | 3 | 2 | 30
Finance | Advanced Financial Operations | US | BFC | Collections and Dispute Management | Best Practice | 20 | 5 | 3 | 3 | 2 | 33
Finance | Advanced Financial Operations | US | 2BE | Convergent Invoicing - Invoice Correction Processing | Best Practice | [5 empty] | 0
Finance | Advanced Financial Operations | US | 2BG | Convergent Invoicing - Invoice Creation for Usage and Service | Best Practice | [5 empty] | 0
Finance | Advanced Financial Operations | US | 3DX | Convergent Invoicing - Management and Rating of Consumption Items | Best Practice | [5 empty] | 0
Finance | Advanced Financial Operations | US | 2T3 | Convergent Invoicing - Recurring and One-Off Items | Best Practice | [5 empty] | 0
Finance | Advanced Financial Operations | US | 42L | Convergent Invoicing - Revenue Sharing and Partner Settlement | Best Practice | [5 empty] | 0
Finance | Advanced Financial Operations | US | 2KF | SAP Fiori Analytical Apps for Convergent Invoicing Specialist | Best Practice | [5 empty] | 0
Finance | Cost Management and Profitability Analysis | US | 3F0 | Event-Based Production Cost Posting | Best Practice | [5 empty] | 0
Finance | Cost Management and Profitability Analysis | US | 1HB | Financial Plan Data Upload from File | Best Practice | 1 | 5 |  | 1 | 1 | 8
Finance | Cost Management and Profitability Analysis | US | 5W2 | Group Valuation | Best Practice | [5 empty] | 0
Finance | Cost Management and Profitability Analysis | US | BEV | Internal Order - Actual | Best Practice | 4 | 2 | 2 | 2 | 0.5 | 10.5
Finance | Cost Management and Profitability Analysis | US | 2ZS | Machine Learning for Monitoring of Goods and Invoice Receipts | Best Practice | [5 empty] | 0
Finance | Cost Management and Profitability Analysis | US | J55 | Margin Analysis | Best Practice | 12 | 2 | 3 | 3 | 1 | 21 | with standard characteristics and without customization
Finance | Cost Management and Profitability Analysis | US | J54 | Overhead Cost Accounting | Best Practice | 6 | 2 | 2 | 2 | 1 | 13
Finance | Cost Management and Profitability Analysis | US | 4Q0 | Predictive Accounting for Travel and Expense Management | Best Practice | [5 empty] | 0
Finance | Cost Management and Profitability Analysis | US | 2I3 | Predictive Commitments Management | Best Practice | [5 empty] | 0
Finance | Cost Management and Profitability Analysis | US | 6VQ | Profit Center Valuation | Best Practice | [5 empty] | 0
Finance | Cost Management and Profitability Analysis | US | BEG | Standard Cost Calculation | Best Practice | 10 | 5 | 2 | 3 | 2 | 22
Finance | Cost Management and Profitability Analysis | US | 34B | Statistical Sales Conditions | Best Practice | [5 empty] | 0
Finance | Cost Management and Profitability Analysis | US | 2QL | Universal Allocation | Best Practice | 6 | 2 | 2 | 2 | 1 | 13
Finance | Enterprise Risk and Compliance | US | 2U3 | Classification for Customs Tariff Number and Commodity Code | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 24J | Compliance Management with SAP Global Trade Services | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 2OH | Continuous Control Monitoring with SAP Process Control | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 2U1 | Customs Management with SAP Global Trade Services | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 1WC | Embargo Control | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 3KY | Financial Operation Monitoring with SAP Financial Compliance | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | BDT | Intrastat Processing | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 2U2 | Key Risk Indicator Monitoring with SAP Risk Management | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 1W8 | Legal Control | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 3JX | Preference Management with SAP Global Trade Services | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 3KX | Privacy Risk Detection with SAP Privacy Governance | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 1WE | Restricted Party Screening with SAP Watch List Screening | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 6NL | Security Risk Detection with SAP Privacy Governance | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 24H | Transfer of Bill of Materials for SAP Global Trade Services | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 24F | Transfer of Contact Person for SAP Global Trade Services | Best Practice | [5 empty] | 0
Finance | Enterprise Risk and Compliance | US | 1WA | Transfer of Primary Master Data for SAP Global Trade Services | Best Practice | [5 empty] | 0
Finance | Environmental Footprint Management | US | 5IM | Product Footprint Management | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | J60 | Accounts Payable | Best Practice | 10 | 3 | 3 | 3 | 3 | 22
Finance | Financial Operations | US | J59 | Accounts Receivable | Best Practice | 10 | 3 | 3 | 3 | 3 | 22
Finance | Financial Operations | US | 4X8 | Advanced Bank Statement Automation | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 1WQ | Bill of Exchange | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 1MV | Cash Application Integration | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 2UV | Combined Invoice – Goods and Service Items | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 2UT | Complementary Invoice – Pricing | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 1S0 | Customer Payments | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 2UW | Delivery of Goods on Behalf of Another Company | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 1S2 | Digital Payments | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 19M | Direct Debit | Best Practice | 5 | 2 |  | 2 | 1 | 10
Finance | Financial Operations | US | 2RP | Electronic Documents | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 43D | Integration with External Tax Calculation Engines | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 1J5 | Invoice, Taxes and Complementary Postings | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 1JT | Lockbox | Best Practice | 3 | 2 |  | 2 | 1 | 8 | Standard BAI2 File
Finance | Financial Operations | US | 2PD | Provisioning of Overdue Receivables | Best Practice | 5 | 2 |  | 2 | 1 | 10
Finance | Financial Operations | US | 55I | Royalties Settlement for Sales | Best Practice | [5 empty] | 0
Finance | Financial Operations | US | 2JB | SAP Fiori Analytical Apps for Financial Accounting | Best Practice | 1 | 3 |  | 2 | 1 | 7
Finance | Financial Operations | US | 4AV | Supplier Financing | Best Practice | [5 empty] | 0
Finance | Real Estate Management | US | 5VX | Enable for Use and Contract Management | Best Practice | [5 empty] | 0
Finance | Real Estate Management | US | 5YU | Enable for Use and Contract Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Real Estate Management | US | 6EG | Enable for Use and Contract Management - Group Ledger IFRS (UPA) | Best Practice | [5 empty] | 0
Finance | Real Estate Management | US | 6EF | Enable for Use and Contract Management (UPA) | Best Practice | [5 empty] | 0
Finance | Real Estate Management | US | 5VY | External Occupancy and Contract Management | Best Practice | [5 empty] | 0
Finance | Real Estate Management | US | 5YV | External Occupancy and Contract Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Real Estate Management | US | 5W0 | Intercompany Occupancy and Contract Management | Best Practice | [5 empty] | 0
Finance | Real Estate Management | US | 5YW | Intercompany Occupancy and Contract Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Real Estate Management | US | 5VZ | Internal Occupancy and Cost Allocation | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 47I | Contract Accounting - Cash Application | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 2DP | Contract Accounting - Company Initiated Payments | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 3L3 | Contract Accounting - Contract-Based Revenue Recognition | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 2BI | Contract Accounting - Customer Initiated Payments | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 2BK | Contract Accounting - Daily and Monthly Closing | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 2SJ | Contract Accounting - External Tax Audit and Compliance Reporting | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 33X | Contract Accounting - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 43Y | Contract Accounting - Integration with Sales Documents | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 6WB | Contract Accounting – Intelligent Collections | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 2AR | Contract Accounting - Master Data and Basic Functions | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 2UJ | Contract Accounting - Open Item Management | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 6WD | Convergent Invoicing - Cost Handling for Subscriptions and Usage | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 6WC | Convergent Invoicing - Intercompany Settlement | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 2KH | SAP Fiori Analytical Apps for Contract Accounting Manager | Best Practice | [5 empty] | 0
Finance | Subscription Billing and Revenue Management | US | 5IK | Subscription Management with Convergent Invoicing | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | J77 | Advanced Bank Account Management | Best Practice | 10 | 2 |  | 2 | 1 | 15
Finance | Treasury Management | US | J78 | Advanced Cash Operations | Best Practice | 40 | 10 | 5 | 5 | 2 | 62
Finance | Treasury Management | US | 4MT | Advanced Payment Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 6B5 | Asset-Backed Securities Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 6B6 | Asset-Backed Securities Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2O0 | Bank Fee Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2NZ | Bank Guarantee Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2O2 | Bank Guarantee Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1EG | Bank Integration with File Interface | Best Practice | 5 | 2 |  | 2 | 1 | 10 | Standard payment file formats with one House bank with 1 payment file type
Finance | Treasury Management | US | 16R | Bank Integration with SAP Multi-Bank Connectivity | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | BFA | Basic Bank Account Management | Best Practice | 10 | 2 |  | 2 | 1 | 15
Finance | Treasury Management | US | BFB | Basic Cash Operations | Best Practice | 10 | 2 |  | 2 | 1 | 15
Finance | Treasury Management | US | 3WY | Bond Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 3WZ | Bond Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1WV | Debt and Investment Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1X7 | Debt and Investment Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1X1 | Foreign Currency Risk Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1X9 | Foreign Currency Risk Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1XD | Hedge Accounting for FX Forward - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 3X1 | Hedge Accounting for FX Forward - Local GAAP | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2RW | Hedge Accounting for FX Option - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 3X2 | Hedge Accounting for FX Option - Local GAAP | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2UF | Hedge Accounting for FX Swap - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 6BP | In-House Banking | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2OI | Intercompany Debt and Investment Mgmt - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2HU | Intercompany Foreign Exchange - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2F2 | Intercompany Foreign Exchange Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1YI | Intercompany Process for Debt and Investment Mgmt | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1X3 | Interest Rate Derivatives Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1XB | Interest Rate Derivatives Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 49D | Letter of Credit Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 49E | Letter of Credit Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 3L5 | Liquidity Planning | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1XN | Market Rates Management - Manually via Upload | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2UN | Money Market Mutual Fund Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 2UO | Money Market Mutual Fund Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 1MN | SAP Fiori Analytical Apps for Treasury and Risk Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 6ND | Securities Option Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 6NE | Securities Option Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 5WF | Shareholding Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 5WG | Shareholding Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 5OD | Stock Management | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 5OE | Stock Management - Group Ledger IFRS | Best Practice | [5 empty] | 0
Finance | Treasury Management | US | 34P | Treasury Workstation Cash Integration | Best Practice | [5 empty] | 0
Human Resources | Core HR and Time Recording | US | 1FD | Employee Integration - SAP S/4HANA Enablement | Best Practice
IT Management | Administration and Usability | US | 1LQ | Output Management | Best Practice
Manufacturing | Manufacturing Operations | US | 2QW | Analytics for Production Unit - Plan/Actual Production Cost | Best Practice | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
Manufacturing | Manufacturing Operations | US | 4R8 | Engineer-to-Order Production with Variant Configuration | Best Practice | 5 | 7 | 7 | 2 | 1 | 22
Manufacturing | Manufacturing Operations | US | 3UK | Inbound Storage Tank Management - Process Manufacturing | Best Practice | 1 | 2 | 2 | 0.5 | 0.5 | 6
Manufacturing | Manufacturing Operations | US | BJE | Make-to-Order Production - Finished Goods Sales and Final Assembly | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 3OK | Make-to-Order Production - Process Manufacturing | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 1BM | Make-to-Order Production - Semifinished Goods Planning and Assembly | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 4OC | Make-to-Order Production for Sales Kits with Variant Configuration | Best Practice | 5 | 7 | 7 | 2 | 1 | 22
Manufacturing | Manufacturing Operations | US | 1YT | Make-to-Order Production with Variant Configuration | Best Practice | 5 | 7 | 7 | 2 | 1 | 22
Manufacturing | Manufacturing Operations | US | BJ8 | Make-to-Stock - Process Manufacturing Based on Process Order | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 2UG | Make-to-Stock - Process Manufacturing Based on Production Order | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | BJ5 | Make-to-Stock Production - Discrete Manufacturing | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 21D | Make-to-Stock Production with Variant Configuration | Best Practice | 5 | 7 | 7 | 2 | 1 | 22
Manufacturing | Manufacturing Operations | US | 3L7 | Make-to-Stock with Co- and By-Products - Process Manufacturing | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 3UL | Make-to-Stock with Silo Material - Process Manufacturing | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 20N | Predictive Analytics Model Training - Supply Chain | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 1Y5 | Production Operations with Manufacturing Execution System | Best Practice | 5 | 7 | 7 | 2 | 1 | 22
Manufacturing | Manufacturing Operations | US | 2JN | Production Operations with SAP Manufacturing Execution | Best Practice | 5 | 7 | 7 | 2 | 1 | 22
Manufacturing | Manufacturing Operations | US | BJK | Production Subcontracting - External Processing | Best Practice | 1 | 2 | 2 | 0.5 | 0.5 | 6
Manufacturing | Manufacturing Operations | US | BJN | Rework Processing - Stock-Manufactured Material | Best Practice | 1 | 2 | 2 | 0.5 | 0.5 | 6
Manufacturing | Manufacturing Operations | US | BJQ | Rework Processing - Work-in-Process | Best Practice | 1 | 2 | 2 | 0.5 | 0.5 | 6
Manufacturing | Manufacturing Operations | US | 42N | Tank Trailer Filling with Residuals | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | 2EM | Just-In-Time Supply to Customer | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Manufacturing Options | US | 53X | Just-In-Time Supply to Customer with Delivery Confirmation | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Manufacturing Options | US | BJH | Make-to-Stock Production - Repetitive Manufacturing | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | 1E3 | Material Replenishment with Kanban - External Procurement | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Manufacturing Options | US | 4B3 | Material Replenishment with Kanban - In-House Production | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Manufacturing Options | US | 4B4 | Material Replenishment with Kanban - Stock Transfer | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Manufacturing Options | US | BMY | Subcontracting | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | 5I2 | Subcontracting with SAP Business Network | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Production Engineering | US | 3LO | Change Manufacturing Bill of Material for Production | Best Practice | 1 | 2 | 2 | 0.5 | 0.5 | 6
Manufacturing | Production Engineering | US | 3LP | Mass Change Manufacturing Bill of Material for Production | Best Practice | 1 | 2 | 2 | 0.5 | 0.5 | 6
Manufacturing | Production Planning | US | 1Y2 | Demand-Driven Buffer Level Management | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Production Planning | US | 2QI | Demand-Driven Replenishment Planning and Execution | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Production Planning | US | J44 | Material Requirements Planning | Best Practice | 5 | 7 | 7 | 2 | 1 | 22
Manufacturing | Production Planning | US | 65D | MRP Change Request Integration with SAP Business Network | Best Practice | 5 | 7 | 7 | 2 | 1 | 22
Manufacturing | Production Planning | US | 4B5 | Predictive Material and Resource Planning | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Production Planning | US | 31L | Production Capacity Evaluation | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Production Planning | US | 3LQ | Production Capacity Leveling | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Quality Management | US | 2QN | Nonconformance Management | Best Practice | 1 | 2 | 2 | 0.5 | 0.5 | 6
Manufacturing | Quality Management | US | 2F9 | Quality Management for Complaints Against Suppliers | Best Practice | 1 | 2 | 2 | 0.5 | 0.5 | 6
Manufacturing | Quality Management | US | 2FA | Quality Management for Complaints from Customers | Best Practice | 1 | 2 | 2 | 0.5 | 0.5 | 6
Manufacturing | Quality Management | US | 1E1 | Quality Management in Discrete Manufacturing | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Quality Management | US | 1FM | Quality Management in Procurement | Best Practice | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Quality Management | US | 1MP | Quality Management in Sales | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Quality Management | US | 1MR | Quality Management in Stock Handling | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Quality Management | US | 2QP | Quality Management of Internal Problems | Best Practice | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Quality Management | US | 2V0 | SAP Fiori Analytical Apps for Quality Management | Best Practice | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
R&D/Engineering | Product Compliance | US | 3FC | Assess Dangerous Goods for a Product | Best Practice
R&D/Engineering | Product Compliance | US | 31H | Assess Marketability of a Product | Best Practice
R&D/Engineering | Product Compliance | US | 31G | Chemical Compliance Approval for Purchased Material and Supplier | Best Practice
R&D/Engineering | Product Compliance | US | 31J | Chemical Compliance in the Value Chain | Best Practice
R&D/Engineering | Product Compliance | US | 3G8 | Dangerous Goods in the Value Chain | Best Practice
R&D/Engineering | Product Compliance | US | 6MT | Label Management | Best Practice
R&D/Engineering | Product Compliance | US | 3VR | Manage Safety Data Sheets for Products | Best Practice
R&D/Engineering | Product Compliance | US | 3VQ | Safety Data Sheets in the Value Chain | Best Practice
R&D/Engineering | Product Compliance | US | 4OL | Substance Volume Tracking | Best Practice
R&D/Engineering | Product Compliance | US | 5OJ | Supplier Compliance in the Value Chain | Best Practice
R&D/Engineering | Product Engineering | US | 1NR | Engineering Bill of Material - Versions Management | Best Practice
R&D/Engineering | Product Engineering | US | 22P | Manage Documents | Best Practice
R&D/Engineering | Product Engineering | US | 2XU | Procurement of Materials with Variant Configuration | Best Practice
R&D/Engineering | Product Engineering | US | 3ND | Product Structure Management | Best Practice
R&D/Engineering | Product Engineering | US | 35Q | Product Structure Template Management | Best Practice
R&D/Engineering | Product Engineering | US | 6W9 | Set Up Advanced Solution Bundle | Best Practice
R&D/Engineering | Product Engineering | US | 22T | Set Up Configurable Model using Variant Configuration | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 22R | Advanced Ingredient Replacement for Recipes | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 64F | Bill of Material Management | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 6OT | Bill of Material Management Professional | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 2G6 | Embedded Software Management | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 1QC | Formulation - Recipe Development | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 2WK | Handover of Product Information to SAP Asset Intelligence Network | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 2YC | Intelligent Content Processing for Document Classification | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 5QC | Product Change Management with Change Records - Process Industries | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 64E | Product Change Mgmt with Change Records - Discrete Industries | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 1QG | Recipe Handover to Production - Bill of Material | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 2G5 | Software Compatibility Management | Best Practice
R&D/Engineering | Product Lifecycle Management | US | 1QA | Specification Management for Recipes | Best Practice
Sales | Order and Contract Management | US | 5D2 | Advanced Intercompany Sales | Best Practice | 6 | 3 | 2 | 3 | 1 | 15
Sales | Order and Contract Management | US | 2QS | Analytics for Sales - Central Stock with Returns | Best Practice | 0 | 1 | 0 | 1 | 0.5 | 2.5
Sales | Order and Contract Management | US | 4A1 | Automation of Order-to-Invoice with SAP Business Network | Best Practice | 3 | 5 | 4 | 3 | 1 | 16 | This solution process is excluded from default activation (efforts from Ariba, basis, abap are required)
Sales | Order and Contract Management | US | 6JM | Basic Business Process Scheduling | Best Practice | 2 | 1 | 1 | 1 | 1 | 6
Sales | Order and Contract Management | US | 4X9 | Create Sales Orders from Unstructured Data | Best Practice | 2 | 4 | 1 | 3 | 0.5 | 10.5 | BTP consultant efforts are required
Sales | Order and Contract Management | US | 1EZ | Credit Memo Processing | Best Practice | 2 | 1 | 1 | 1 | 0.5 | 5.5 | Technical efforts are required for workflow logic
Sales | Order and Contract Management | US | 1IU | Customer Consignment | Best Practice | 3 | 3 | 2 | 3 | 1 | 12
Sales | Order and Contract Management | US | BKP | Customer Returns | Best Practice | 4 | 4 | 2 | 3 | 1 | 14 | multiple types of return scenarios with workflows, technical efforts required for workflows setup
Sales | Order and Contract Management | US | 3TE | Customer Returns for Non-Stock and Service Materials | Best Practice | 3 | 3 | 1 | 2 | 1 | 10
Sales | Order and Contract Management | US | 5CX | Customer Returns for Sales Kits | Best Practice | 3 | 3 | 1 | 2 | 1 | 10
Sales | Order and Contract Management | US | 1Z3 | Customer Returns with Direct Shipment from Customer to Supplier | Best Practice | 3 | 3 | 1 | 2 | 1 | 10
Sales | Order and Contract Management | US | 1F1 | Debit Memo Processing | Best Practice | 1 | 1 | 0.5 | 1 | 0.5 | 4
Sales | Order and Contract Management | US | 1MI | Delivery Processing Without Order Reference | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | 1Z1 | Digital Payments - Sales | Best Practice | 5 | 6 | 4 | 3 | 1 | 19 | Technical efforts ffor integration with the payment hub for authorization when creating sales documents sales side 3 scenarios, integration of BP,SO with payment hub for authorization, reauthorization, verification, cancellation...
Sales | Order and Contract Management | US | 1Z6 | External Billing | Best Practice | 2 | 3 | 2 | 1 | 1 | 9 | Technical efforts -use of the external billing interface to create billing documents
Sales | Order and Contract Management | US | BKA | Free Goods Processing | Best Practice | 1 | 1 | 1 | 1 | 0.5 | 4.5
Sales | Order and Contract Management | US | BDA | Free of Charge Delivery | Best Practice | 1 | 1 | 1 | 1 | 0.5 | 4.5
Sales | Order and Contract Management | US | 2EL | Integration of Sales with External Buyers | Best Practice | 4 | 4 | 5 | 3 | 2 | 18 | Technical efforts are required for interfaces (APIs) to simplify and automate exchanging sales documents and their follow-on messages for below processes enable B2B integration with the corresponding Integration of SAP S/4HANA Cloud Procurement with Suppliers (2EJ) scope item (Prerequisites-PO must have been created and automatically sent to the SAP S/4HANA system (supplier side) An Order Confirmation is automatically sent to the Buyer system An Order Confirmation Change is automatically sent to the Buyer system ASN is automatically sent to the Buyer system, Invoice is sent to the Buyer system.
Sales | Order and Contract Management | US | BKL | Invoice Correction Process with Credit Memo | Best Practice | 1 | 1 | 0.5 | 0.5 | 0.5 | 3.5 | with workflows
Sales | Order and Contract Management | US | BDQ | Invoice Correction Process with Debit Memo | Best Practice | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | without workflows
Sales | Order and Contract Management | US | BDD | Lean Customer Returns | Best Practice | 2 | 1 | 1 | 1 | 1 | 1
Sales | Order and Contract Management | US | 1MC | Omnichannel Convergent Billing | Best Practice | 1 | 1 | 2 | 1 | 1 | 6
Sales | Order and Contract Management | US | BKN | Order-to-Cash Performance Monitoring | Best Practice | 0.5 | 1 | 0 | 1 | 0.5 | 3
Sales | Order and Contract Management | US | 1O0 | Planning Apps for Sales | Best Practice | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
Sales | Order and Contract Management | US | 2YJ | Predictive Analytics Model Training - Sales | Best Practice | 0.5 | 2 | 0 | 1 | 0.5 | 4
Sales | Order and Contract Management | US | BDW | Returnables Processing | Best Practice | 2 | 2 | 1 | 1 | 1 | 7
Sales | Order and Contract Management | US | 2EQ | Sale of Services | Best Practice | 2 | 2 | 1 | 1 | 1 | 7 | sale of service with credit management
Sales | Order and Contract Management | US | 2TT | Sales Commissions - External Sales Representative | Best Practice | 5 | 5 | 2 | 4 | 2 | 18 | sales commissions -multiple business processes, with workflows
Sales | Order and Contract Management | US | I9I | Sales Contract Management | Best Practice | 3 | 3 | 1 | 2 | 1 | 10 | To update down payment status of sales contracts, you need to finish the bgRFC configuration activities described sales contract management with downpayments
Sales | Order and Contract Management | US | 1IQ | Sales Inquiry | Best Practice | 1 | 1 | 0 | 0.5 | 0.5 | 3
Sales | Order and Contract Management | US | BDN | Sales of Non-Stock Item with Order-Specific Procurement | Best Practice | 2 | 3 | 2 | 1 | 1 | 9 | including workflows for purchase orders. credit mgt and other optional steps not considered
Sales | Order and Contract Management | US | BDH | Sales Order Entry with One-Time Customer | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | BKK | Sales Order Fulfillment Monitoring and Operations | Best Practice | 1 | 1 | 1 | 1 | 1 | 5 | 14 reports in this scope id
Sales | Order and Contract Management | US | BKX | Sales Order Processing - SEPA Direct Debit Handling | Best Practice | [5 empty] | 0 | Not applicable for USA best practices
Sales | Order and Contract Management | US | 2ET | Sales Order Processing for Non-Stock Material | Best Practice | 2 | 2 | 1 | 2 | 1 | 8 | iefforts included of credit managment and POD
Sales | Order and Contract Management | US | 31Q | Sales Order Processing for Sales Kits | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | BKJ | Sales Order Processing with Customer Down Payment | Best Practice | 2 | 2 | 1 | 1 | 1 | 7 | Basis efforts are required as per setup instructions guide
Sales | Order and Contract Management | US | BKZ | Sales Order Processing with Invoice List and Collective Billing | Best Practice | 1 | 1 | 1 | 1 | 1 | 5 | two scenarios included for invoice lists and collective invoicing
Sales | Order and Contract Management | US | BD3 | Sales Processing using Third-Party with Shipping Notification | Best Practice | 2 | 2 | 2 | 1 | 1 | 8 | considered workflows for sales order and purchase orders only no credit management
Sales | Order and Contract Management | US | 4R6 | Sales Processing using Third-Party with Variant Configuration | Best Practice | 4 | 4 | 2 | 2 | 1 | 13 | This solution requires additional licenses
Sales | Order and Contract Management | US | BDK | Sales Processing Using Third-Party Without Shipping Notification | Best Practice | 2 | 2 | 2 | 1 | 1 | 8 | considered workflows for sales order and purchase orders only no credit management
Sales | Order and Contract Management | US | BDG | Sales Quotation | Best Practice | 3 | 2 | 1 | 1 | 1 | 8 | quotations with workflows
Sales | Order and Contract Management | US | 1B6 | Sales Rebate Processing | Best Practice | 5 | 5 | 3 | 3 | 2 | 18 | sales rebates with one customer, two steps settlement, multipe customers, workflows, sales rebates with fixed amount
Sales | Order and Contract Management | US | 4LZ | Sales Scheduling Agreement with Consignment | Best Practice | 4 | 4 | 3 | 2 | 1 | 14 | integration with buyer system for storing purchase order info in sales order-efforts of ABAP and basis are required. EDI are required for ASN,Invoice and credit memo
Sales | Order and Contract Management | US | 3NR | Sales Scheduling Agreements | Best Practice | 3 | 3 | 3 | 2 | 1 | 12 | integration with buyer system for storing purchase order info in sales order-efforts of ABAP and basis are required. EDI are required for ASN,Invoice also includes configuration of set up guide (38 pages)
Sales | Order and Contract Management | US | 6KO | SAP Customer Experience Entities with SAP Service and Sales Cloud | Best Practice | 2 | 3 | 3 | 1 | 1 | 10 | Basis and ABAP efforts are required as per setup guide to integration between SAP S/4HANA and SAP Sales Cloud and SAP Service Cloud Version 2 using SAP Cloud Integration related to business partners, company code, sales organization, materials, funcional location, equipment, sales quote
Sales | Order and Contract Management | US | 1BS | SAP Fiori Analytical Apps for Sales | Best Practice | 1 | 3 | 1 | 2 | 1 | 8 | 16 reports considered in scope
Sales | Order and Contract Management | US | 4H2 | Self-Billing | Best Practice | 2 | 3 | 4 | 3 | 1 | 13 | This solution process is excluded from default activation integrate SAP S/4HANA system with SAP Self-Billing Cockpit. SAP Self-Billing Cockpit is licensed in the SAP Store. efforts required from basis, abap efforts from sales side is given considering sell from stock scenario and integration testing efforts
Sales | Order and Contract Management | US | BD9 | Sell from Stock | Best Practice | 4 | 4 | 3 | 3 | 2 | 16 | efforts are considered for sales order with workflows, credit management, POD, batch mgt, serial numbers
Sales | Order and Contract Management | US | 5MQ | Sell from Stock with Valuated Stock in Transit | Best Practice | 2 | 2 | 1 | 1 | 1 | 7
Sales | Order and Contract Management | US | 57Z | Subscription Management with Sales Billing | Best Practice | 2 | 3 | 2 | 2 | 1 | 10 | ABAP and basis efforts required for integratiing SAP Subscription billing with S/4HANA for billing
Sales | Sales Force Support | US | 41V | Presales Management | Best Practice | [6 empty] | This is not in scope ofbest practices 2302 SP02, Prviate Cloud
Sales | Solution Business Management | US | 4Q5 | Solution Quotation | Best Practice | 2 | 2 | 2 | 1 | 1 | 8 | prerequisite- Service Order Management, Service Contract Management must be implemented
Service | Service Master Data & Agreement Management | US | 6AU | Service with Advanced Execution | Best Practice | 3 | 2 | 2 | 2 | 1 | 10
Service | Service Master Data & Agreement Management | US | 6F1 | Recurring Services with Advanced Execution | Best Practice | 2 | 3 | 2 | 2 | 1 | 10
Service | Service Master Data & Agreement Management | US | 426 | Service Contract Management | Best Practice | 2 | 2 | 1 | 2 | 1 | 8
Service | Service Master Data & Agreement Management | US | 43B | Service Monitoring and Analytics | Best Practice | 3 | 2 | 2 | 1 | 1 | 9
Service | Service Master Data & Agreement Management | US | 63Y | Warranty Claim Management - Customer Claim Processing | Best Practice | 3 | 2 | 2 | 2 | 1 | 10
Service | Service Master Data & Agreement Management | US | 5HR | Warranty Claim Management - Supplier Recovery Processing | Best Practice | 4 | 3 | 2 | 2 | 2 | 13
Service | Service Operations & Processes | US | 3XK | In-House Repair | Best Practice | 4 | 3 | 2 | 2 | 2 | 13
Service | Service Operations & Processes | US | 41W | Interaction Center Service Request Management | Best Practice | 2 | 2 | 1 | 2 | 1 | 8
Service | Service Operations & Processes | US | 4X5 | Recurring Services | Best Practice | 2 | 2 | 1 | 2 | 1 | 8
Service | Service Operations & Processes | US | 41Z | Service Order Management | Best Practice | 3 | 2 | 1 | 2 | 1 | 9
Solutions for Specific Industries | Automotive | US | 5ON | Digital Vehicle | Best Practice
Solutions for Specific Industries | Oil and Gas | US | 6VA | Field Logistics Analytics | Best Practice
Solutions for Specific Industries | Oil and Gas | US | 40G | Field Logistics Planning and Execution | Best Practice
Solutions for Specific Industries | Oil and Gas | US | 6BA | Field Logistics Planning and Execution - Containers and Voyages | Best Practice
Solutions for Specific Industries | Oil and Gas | US | 5OM | Field Logistics Planning and Execution – Direct Procurement | Best Practice
Solutions for Specific Industries | Oil and Gas | US | 4AH | Field Logistics Planning and Execution – Supplier Items | Best Practice
Sourcing and Procurement | Central Procurement | US | 4QN | Central Procurement with SAP Ariba Sourcing | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 2ME | Central Purchase Contracts | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 2XT | Central Purchasing | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 1XI | Central Requisitioning | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 4B0 | Contract for Central Procurement with SAP Ariba Contracts | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 4RD | Direct Material Sourcing | Best Practice | 2 | 2 | 3 | 2 | 1 | 10 | Additional license & Integration effort needed
Sourcing and Procurement | Invoice Management | US | 1L2 | Supplier Quote automation with SAP Ariba Commerce Automation | Best Practice | [5 empty] | 0 | This is not existing in best practices 2302 SP02, Private Cloud
Sourcing and Procurement | Invoice Management | US | J82 | Automated Purchase-to-Pay with SAP Ariba Commerce Automation | Best Practice | 2 | 2 | 3 | 2 | 1 | 10 | Additional license & Integration effort needed
Sourcing and Procurement | Invoice Management | US | 2TW | Complementary Procurement Functions | Best Practice | 1 | 1 | 2 | 1 | 1 | 6
Sourcing and Procurement | Invoice Management | US | BNX | Consumable Purchasing | Best Practice | 2 | 1 | 2 | 2 | 1 | 8 | Technical effort for Workflow is required
Sourcing and Procurement | Invoice Management | US | 2TX | Direct Procurement with Inbound Delivery | Best Practice | 2 | 1 | 2 | 2 | 1 | 8
Sourcing and Procurement | Invoice Management | US | 22K | External Workforce Procurement via SAP Fieldglass | Best Practice | 2 | 2 | 3 | 2 | 1 | 10 | Additional license & Integration effort needed
Sourcing and Procurement | Invoice Management | US | 4N6 | Invoice Processing with SAP Central Invoice Management | Best Practice | [5 empty] | 0 | This is not existing in best practices 2302 SP02, Private Cloud
Sourcing and Procurement | Invoice Management | US | J45 | Procurement of Direct Materials | Best Practice | 3 | 1 | 2 | 2 | 1 | 9 | Technical effort for Workflow is required
Sourcing and Procurement | Invoice Management | US | 22Z | Procurement of Services | Best Practice | 3 | 1 | 2 | 2 | 1 | 9 | Technical effort for Workflow is required
Sourcing and Procurement | Invoice Management | US | 18J | Requisitioning | Best Practice | 3 | 1 | 2 | 2 | 1 | 9 | Technical effort for Workflow is required
Sourcing and Procurement | Invoice Management | US | 2UU | Returnable Packaging to Vendor | Best Practice | [5 empty] | 0
Sourcing and Procurement | Invoice Management | US | 4R2 | Service Procurement with SAP Business Network and SAP Fieldglass | Best Practice | 2 | 2 | 3 | 2 | 1 | 10 | Additional license & Integration effort needed
Sourcing and Procurement | Invoice Management | US | 2LG | Supplier Consignment | Best Practice | 1 | 1 | 1 | 2 | 1 | 6
Sourcing and Procurement | Operational Procurement | US | 5JT | Automation of Central Procurement Quote with SAP Business Network | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional license & Integration effort needed
Sourcing and Procurement | Operational Procurement | US | 42K | Automation of Source-to-Pay with SAP Business Network | Best Practice | 2 | 2 | 3 | 2 | 1 | 10 | Additional license & Integration effort needed
Sourcing and Procurement | Operational Procurement | US | BLF | Batch Management | Best Practice | 2 | 1 | 3 | 2 | 1 | 9 | Batch integration required from PP and SD
Sourcing and Procurement | Operational Procurement | US | 2NV | Guided Buying Capability with SAP Ariba Buying | Best Practice | 2 | 2 | 3 | 2 | 1 | 10 | Additional license & Integration effort needed
Sourcing and Procurement | Operational Procurement | US | 3EN | Guided Buying for Central Procurement with SAP Ariba Buying | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional license & Integration effort needed
Sourcing and Procurement | Operational Procurement | US | 2EJ | Integration of Procurement with External Suppliers | Best Practice | [5 empty] | 0
Sourcing and Procurement | Operational Procurement | US | 1QR | Predictive Analytics for Purchase Contract Quantity Consumption | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Operational Procurement | US | 41F | Procurement of Pipeline Materials | Best Practice | 2 | 1 | 2 | 1 | 1 | 7
Sourcing and Procurement | Operational Procurement | US | 2R7 | Purchasing Rebate Processing | Best Practice | 3 | 2 | 2 | 2 | 1 | 10
Sourcing and Procurement | Operational Procurement | US | 2NY | Scheduling Agreement for Consignment Procurement | Best Practice | 3 | 1 | 1 | 2 | 1 | 8
Sourcing and Procurement | Operational Procurement | US | 2NX | Scheduling Agreement for Subcontracting Procurement | Best Practice | 3 | 1 | 2 | 2 | 1 | 9
Sourcing and Procurement | Operational Procurement | US | BMR | Scheduling Agreements in Procurement | Best Practice | 2 | 1 | 2 | 2 | 1 | 8
Sourcing and Procurement | Operational Procurement | US | 2XW | Proposal of New Catalog Item | Best Practice | [5 empty] | 0
Sourcing and Procurement | Operational Procurement | US | 30W | Proposal of Options for materials without purchase contract | Best Practice | [5 empty] | 0
Sourcing and Procurement | Operational Procurement | US | BLL | Serial Number Management | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Procurement Analytics | US | 2QU | Analytics - Purchase Order Visibility and Procurement Spend | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Procurement Analytics | US | 1JI | Real-Time Reporting and Monitoring for Procurement | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Sourcing and Contract Management | US | 3ZF | Central Sourcing | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional license & Integration effort needed
Sourcing and Procurement | Sourcing and Contract Management | US | 4AZ | Contract Management with SAP Ariba Contracts | Best Practice | 2 | 2 | 3 | 2 | 1 | 10 | Additional license & Integration effort needed
Sourcing and Procurement | Sourcing and Contract Management | US | 6AN | Contract Price Renegotiation | Best Practice | 2 | 2 | 3 | 2 | 1 | 10 | Additional license & Integration effort needed
Sourcing and Procurement | Sourcing and Contract Management | US | 2OQ | Integration to SAP Enterprise Contract Assembly | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Sourcing and Contract Management | US | 4RI | Preferred Supplier List | Best Practice | [5 empty] | 0
Sourcing and Procurement | Sourcing and Contract Management | US | 6AJ | Procurement Planning Integration with Product Sourcing | Best Practice | [5 empty] | 0
Sourcing and Procurement | Sourcing and Contract Management | US | BMD | Purchase Contract | Best Practice | 2 | 1 | 2 | 2 | 1 | 8
Sourcing and Procurement | Sourcing and Contract Management | US | 1XF | Request for Price | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Sourcing and Contract Management | US | 1XV | SAP S/4HANA for Enterprise Contract Management | Best Practice | 2 | 1 | 2 | 2 | 1 | 8
Sourcing and Procurement | Sourcing and Contract Management | US | 4BL | Sourcing with SAP Ariba Sourcing | Best Practice | 2 | 2 | 3 | 2 | 1 | 10 | Additional license & Integration effort needed
Sourcing and Procurement | Supplier Management | US | 19C | Activity Management in Procurement | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Supplier Management | US | 3FY | Prediction of Delivery Date for Purchase Order Items | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Supplier Management | US | 19E | Supplier Classification and Segmentation | Best Practice | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Supplier Management | US | SL4 | Supplier Evaluation and Performance Monitoring | Best Practice | 2 | 1 | 1 | 2 | 1 | 7
Sourcing and Procurement | Product Engineering | US | 43E | Intelligent Approval Workflow | Best Practice | [5 empty] | 0 | This is not existing in best practices 2302 SP02, Private Cloud
Sourcing and Procurement | Product Engineering | US | 2XU | Procurement of Materials with Variant Configuration | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Integration with SD and PP
Supply Chain | Advanced Order Promising | US | 1JW | Advanced Available-to-Promise Processing | Best Practice | 8 | 8 | 4 | 4 | 2 | 26 | This solution requires additional license
Supply Chain | Advanced Order Promising | US | 6JM | Basic Business Process Scheduling | Best Practice | 1 | 1 | 0 | 1 | 0.5 | 3.5
Supply Chain | Advanced Transportation | US | 4OZ | Planning of External Transportation Requirements | Best Practice | 3 | 3 | 4 | 2 | 1 | 13
Supply Chain | Advanced Warehousing | US | 1VD | Advanced Warehouse Outbound Processing to Customer | Best Practice | 2 | 2 | 2 | 2 | 1 | 9 | This solution requires additional license
Supply Chain | Inventory | US | BMC | Core Inventory Management | Best Practice | 2 | 2 | 2 | 2 | 1 | 9
Supply Chain | Inventory | US | 4LO | Enablement of SAP Excise Tax Management | Best Practice | 2 | 2 | 2 | 2 | 1 | 9
Supply Chain | Inventory | US | 4LU | Physical Inventory - Cycle Counting | Best Practice | 2 | 2 | 2 | 1 | 1 | 8
Supply Chain | Inventory | US | BML | Physical Inventory - Inventory Count and Adjustment | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Inventory | US | BMK | Return to Supplier | Best Practice | 2 | 2 | 2 | 2 | 1 | 9
Supply Chain | Logistics Cross Topics | US | 4MM | Handling Unit Management | Best Practice | 2 | 2 | 2 | 2 | 1 | 9
Supply Chain | Order Promising | US | 6LJ | Available-to-Promise Processing | Best Practice | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | 1FS | Basic Warehouse Inbound Processing from Supplier | Best Practice | 2 | 2 | 2 | 1 | 1 | 8
Supply Chain | Warehousing | US | 1V9 | Basic Warehouse Inbound Processing from Supplier with Quality Management | Best Practice | 2 | 2 | 2 | 1 | 1 | 8
Supply Chain | Warehousing | US | 1G2 | Basic Warehouse Outbound Processing to Customer | Best Practice | 2 | 2 | 2 | 1 | 1 | 8
Supply Chain | Warehousing | US | 4RQ | Decentralized EWM - Ad Hoc Goods Issue | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional setup required
Supply Chain | Warehousing | US | 4RO | Decentralized EWM - Inbound Processing | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional setup required
Supply Chain | Warehousing | US | 4RP | Decentralized EWM - Outbound Processing | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional setup required
Supply Chain | Warehousing | US | 4RR | Decentralized EWM - Physical Inventory | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional setup required
Supply Chain | Warehousing | US | 4RS | Decentralized EWM - Replenishment | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional setup required
Supply Chain | Warehousing | US | 4UA | Decentralized EWM - Technical Integration ERP | Best Practice | 3 | 2 | 3 | 2 | 1 | 11 | Additional setup required
Supply Chain | Warehousing | US | 1FU | Initial Stock Upload for Warehouse | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Warehousing | US | 1FW | Physical Inventory in Warehouse | Best Practice | 2 | 2 | 2 | 1 | 1 | 8
Supply Chain | Warehousing | US | 1VB | Production Integration - Component Consumption and Receipt in Warehouse | Best Practice | 2 | 2 | 2 | 1 | 1 | 8
Supply Chain | Warehousing | US | 1FY | Replenishment in Warehouse | Best Practice | 2 | 2 | 2 | 1 | 1 | 8
Supply Chain | Warehousing | US | BGG | SAP Fiori Analytical Apps for Inventory and Warehouse Management | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Warehousing | US | 1G0 | Scrapping in Warehouse | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Warehousing | US | 1V5 | Warehouse Inbound Processing from Supplier with Batch Management | Best Practice | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | 1V7 | Warehouse Outbound Processing to Customer with Batch Management | Best Practice | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Quality Management | US | 1MR | Quality Management in Stock Handling | Best Practice | 2 | 2 | 2 | 1 | 1 | 8
Supply Chain | Warehousing | US | 2LN | Basic Avalibale to promise processing | Best Practice | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Quality Management | US | 2FA | Quality Management for Complaints from Customers | Best Practice | 2 | 2 | 2 | 1 | 1 | 8
Supply Chain | Inventory | US | 2UU | Returnable Packaging | Best Practice | [5 empty] | 0

## YASH BP
Line of Business | Business Area | Country/Region Key | Scope ID | Scope ID Description | Complexity | Wokshops & Configuration | Unit Testing | Integration Testing | Documentation, Training core User | User Acceptance Testing | Total | Comments
Application Platform and Infrastructure | Process Management and Integration | US | 1NN | Business Event Handling | Non BP
Application Platform and Infrastructure | Process Management and Integration | US | 1NJ | Responsibility Management | Non BP
Application Platform and Infrastructure | Process Management and Integration | US | 31N | Situation Handling | Non BP
Asset Management | Maintenance Management | US | BH1 | Corrective Maintenance (successor: 4HH) | Non BP | 1 | 3 | 3 | 1 | 1 | 9
Asset Management | Maintenance Management | US | BH2 | Emergency Maintenance (successor: 4HH) | Non BP | 1 | 2 | 2 | 1 | 1 | 7
Asset Management | Maintenance Management | US | 43R | Maintenance Resource Scheduling | Non BP | 2 | 4 | 4 | 2 | 1 | 13
Asset Management | Maintenance Management | US | BJ2 | Preventive Maintenance (successor: 4HI) | Non BP | 2 | 4 | 4 | 2 | 1 | 13
Asset Management | Maintenance Management | US | 4HI | Proactive Maintenance | Non BP | 2 | 4 | 4 | 2 | 1 | 13
Asset Management | Maintenance Management | US | 4HH | Reactive Maintenance | Non BP | 2 | 4 | 4 | 2 | 1 | 13
Database and Data Management | Enterprise Information Management | US | 2Q2 | Data Migration to SAP S/4HANA from Staging | Non BP
Database and Data Management | Enterprise Information Management | US | 1I9 | Master Data Catalog for SAP S/4HANA - On-premise | Non BP
Finance | Accounting and Financial Close | US | J58 | Accounting and Financial Close | Non BP | 15 | 5 | 2 | 6 | 2 | 30 | Enterprise setup, COA Finalization, Reporting structures, approvals, Period endclosing
Finance | Accounting and Financial Close | US | 1GA | Accounting and Financial Close - Group Ledger IFRS | Non BP | 3 | 2 | 1 | 2 | 0.5 | 8.5
Finance | Accounting and Financial Close | US | 2FD | Accounting for Incoming Sales Orders | Non BP | 6 | 2 | 3 | 2 | 1 | 14 | Predictive accounting, extension ledgers
Finance | Accounting and Financial Close | US | 33Q | Actual Costing | Non BP | 15 | 5 | 5 | 3 | 2 | 30 | Efforts depends on no.of plants and plant specific requirements
Finance | Accounting and Financial Close | US | J62 | Asset Accounting | Non BP | 10 | 5 | 3 | 3 | 1 | 22
Finance | Accounting and Financial Close | US | 1GB | Asset Accounting - Group Ledger IFRS | Non BP | 3 | 2 | 1 | 2 | 0.5 | 8.5
Finance | Accounting and Financial Close | US | 6DS | Asset Accounting - Group Ledger IFRS (UPA) | Non BP | 4 | 2 | 2 | 2 | 0.5 | 10.5
Finance | Accounting and Financial Close | US | 6DR | Asset Accounting (UPA) | Non BP
Finance | Accounting and Financial Close | US | BFH | Asset Under Construction | Non BP | 4 | 2 | 2 | 2 | 0.5 | 10.5
Finance | Accounting and Financial Close | US | 1GF | Asset Under Construction - Group Ledger IFRS | Non BP | 2 | 2 | 1 | 2 | 0.5 | 7.5
Finance | Accounting and Financial Close | US | 6DU | Asset under Construction - Group Ledger IFRS (UPA) | Non BP
Finance | Accounting and Financial Close | US | 6DT | Asset under Construction (UPA) | Non BP
Finance | Accounting and Financial Close | US | 1GO | Cash Journal | Non BP | 2 | 1 |  | 2 | 0.5 | 5.5
Finance | Accounting and Financial Close | US | 1J2 | Compliance Formats - Support Preparation | Non BP
Finance | Accounting and Financial Close | US | 1K2 | Event-Based Revenue Recognition - Sell from Stock | Non BP
Finance | Accounting and Financial Close | US | 33M | Event-Based Revenue Recognition - Sell from Stock - IFRS | Non BP
Finance | Accounting and Financial Close | US | 3M3 | Event-Based Revenue Recognition - Service Documents | Non BP
Finance | Accounting and Financial Close | US | 3M4 | Event-Based Revenue Recognition - Service Documents - IFRS | Non BP
Finance | Accounting and Financial Close | US | 6AK | Event-Based Revenue Recognition - Service with Adv. Execution | Non BP
Finance | Accounting and Financial Close | US | 6AL | Event-Based Revenue Recognition - Service with Adv. Execution - IFRS | Non BP
Finance | Accounting and Financial Close | US | 2OO | External Tax Audit | Non BP
Finance | Accounting and Financial Close | US | 2FM | Financial Planning and Analysis | Non BP
Finance | Accounting and Financial Close | US | 3SS | General Indirect Tax in the Canary Islands | Non BP
Finance | Accounting and Financial Close | US | 1GI | General Ledger Allocation Cycle | Non BP | 5 | 2 |  | 1 | 1 | 9
Finance | Accounting and Financial Close | US | 4RC | Integrated Financial Planning | Non BP | 5 | 2 |  | 1 | 1 | 9
Finance | Accounting and Financial Close | US | 4LG | Intelligent Intercompany Reconciliation | Non BP
Finance | Accounting and Financial Close | US | 40Y | Intercompany Reconciliation Process | Non BP
Finance | Accounting and Financial Close | US | BEJ | Inventory Valuation for Year-End Closing | Non BP | 4 | 2 |  | 1 | 1 | 8
Finance | Accounting and Financial Close | US | 1ZT | Managing Material Price Changes and Inventory Values | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Finance | Accounting and Financial Close | US | 2V7 | Monitoring of Goods and Invoice Receipts | Non BP
Finance | Accounting and Financial Close | US | 4PG | Organizational Flexibility in Financial Accounting | Non BP
Finance | Accounting and Financial Close | US | BF7 | Period-End Closing - Maintenance Orders | Non BP | 3 | 2 | 1 | 1 | 1 | 8
Finance | Accounting and Financial Close | US | BEI | Period-End Closing - Plant | Non BP | 8 | 5 | 2 | 3 | 2 | 20
Finance | Accounting and Financial Close | US | 2VB | Purchase Order Accruals | Non BP
Finance | Accounting and Financial Close | US | 5VW | Revenue Accounting | Non BP
Finance | Accounting and Financial Close | US | 2QY | SAP Fiori Analytical Apps for Asset Accounting in Finance | Non BP | 1 | 2 |  | 1 | 1 | 5
Finance | Accounting and Financial Close | US | BGC | SAP Fiori Analytical Apps for G/L Accounting in Finance | Non BP | 1 | 2 |  | 1 | 1 | 5
Finance | Accounting and Financial Close | US | 63L | Service Entry Sheet Based Accruals | Non BP
Finance | Accounting and Financial Close | US | 6DF | Universal Parallel Accounting | Non BP
Finance | Advanced Accounting and Financial Close | US | 5XU | Document and Reporting Compliance | Non BP | 15 | 10 | 10 | 5 | 5 | 45
Finance | Advanced Accounting and Financial Close | US | 3AF | Group Account Preparation for Financial Consolidation | Non BP
Finance | Advanced Accounting and Financial Close | US | 5PU | Group Financial Planning | Non BP
Finance | Advanced Accounting and Financial Close | US | 4VB | Group Reporting - Consolidation with Multiple Group Currencies | Non BP
Finance | Advanced Accounting and Financial Close | US | 2U6 | Group Reporting - Data from External Systems | Non BP
Finance | Advanced Accounting and Financial Close | US | 287 | Group Reporting - Data from SAP Group Reporting Data Collection | Non BP
Finance | Advanced Accounting and Financial Close | US | 4R7 | Group Reporting - Environmental, Social, and Governance Data | Non BP
Finance | Advanced Accounting and Financial Close | US | 1SG | Group Reporting - Financial Consolidation | Non BP
Finance | Advanced Accounting and Financial Close | US | 3LX | Group Reporting - Matrix Consolidation | Non BP
Finance | Advanced Accounting and Financial Close | US | 28B | Group Reporting - Plan Consolidation | Non BP
Finance | Advanced Accounting and Financial Close | US | 3F7 | Joint Venture Accounting | Non BP
Finance | Advanced Accounting and Financial Close | US | 1T6 | Lease-In Accounting | Non BP
Finance | Advanced Accounting and Financial Close | US | 21P | Lease-In Accounting - Group Ledger IFRS | Non BP
Finance | Advanced Accounting and Financial Close | US | 6EC | Lease-In Accounting - Group Ledger IFRS (UPA) | Non BP
Finance | Advanced Accounting and Financial Close | US | 6EB | Lease-In Accounting (UPA) | Non BP
Finance | Advanced Accounting and Financial Close | US | 21Q | Lease-Out Accounting | Non BP
Finance | Advanced Accounting and Financial Close | US | 2SB | Lease-Out for Sublease Accounting | Non BP
Finance | Advanced Accounting and Financial Close | US | 2SA | Lease-Out for Sublease Accounting - Group Ledger IFRS | Non BP
Finance | Advanced Accounting and Financial Close | US | 6EE | Lease-Out for Sublease Accounting - Group Ledger IFRS (UPA) | Non BP
Finance | Advanced Accounting and Financial Close | US | 6ED | Lease-Out for Sublease Accounting (UPA) | Non BP
Finance | Advanced Accounting and Financial Close | US | 3F4 | Sales-Based Rent | Non BP
Finance | Advanced Accounting and Financial Close | US | 21R | Service Contract | Non BP
Finance | Advanced Financial Operations | US | 1QM | Advanced Credit Management | Non BP | 40 | 5 | 10 | 3 | 2 | 60
Finance | Advanced Financial Operations | US | BD6 | Basic Credit Management | Non BP | 15 | 5 | 5 | 3 | 2 | 30
Finance | Advanced Financial Operations | US | BFC | Collections and Dispute Management | Non BP | 20 | 5 | 3 | 3 | 2 | 33
Finance | Advanced Financial Operations | US | 2BE | Convergent Invoicing - Invoice Correction Processing | Non BP
Finance | Advanced Financial Operations | US | 2BG | Convergent Invoicing - Invoice Creation for Usage and Service | Non BP
Finance | Advanced Financial Operations | US | 3DX | Convergent Invoicing - Management and Rating of Consumption Items | Non BP
Finance | Advanced Financial Operations | US | 2T3 | Convergent Invoicing - Recurring and One-Off Items | Non BP
Finance | Advanced Financial Operations | US | 42L | Convergent Invoicing - Revenue Sharing and Partner Settlement | Non BP
Finance | Advanced Financial Operations | US | 2KF | SAP Fiori Analytical Apps for Convergent Invoicing Specialist | Non BP
Finance | Cost Management and Profitability Analysis | US | 3F0 | Event-Based Production Cost Posting | Non BP
Finance | Cost Management and Profitability Analysis | US | 1HB | Financial Plan Data Upload from File | Non BP | 1 | 5 |  | 1 | 1 | 8
Finance | Cost Management and Profitability Analysis | US | 5W2 | Group Valuation | Non BP
Finance | Cost Management and Profitability Analysis | US | BEV | Internal Order - Actual | Non BP | 4 | 2 | 2 | 2 | 0.5 | 10.5
Finance | Cost Management and Profitability Analysis | US | 2ZS | Machine Learning for Monitoring of Goods and Invoice Receipts | Non BP
Finance | Cost Management and Profitability Analysis | US | J55 | Margin Analysis | Non BP | 12 | 2 | 3 | 3 | 1 | 21 | with standard characteristics and without customization
Finance | Cost Management and Profitability Analysis | US | J54 | Overhead Cost Accounting | Non BP | 6 | 2 | 2 | 2 | 1 | 13
Finance | Cost Management and Profitability Analysis | US | 4Q0 | Predictive Accounting for Travel and Expense Management | Non BP
Finance | Cost Management and Profitability Analysis | US | 2I3 | Predictive Commitments Management | Non BP
Finance | Cost Management and Profitability Analysis | US | 6VQ | Profit Center Valuation | Non BP
Finance | Cost Management and Profitability Analysis | US | BEG | Standard Cost Calculation | Non BP | 10 | 5 | 2 | 3 | 2 | 22
Finance | Cost Management and Profitability Analysis | US | 34B | Statistical Sales Conditions | Non BP
Finance | Cost Management and Profitability Analysis | US | 2QL | Universal Allocation | Non BP | 6 | 2 | 2 | 2 | 1 | 13
Finance | Enterprise Risk and Compliance | US | 2U3 | Classification for Customs Tariff Number and Commodity Code | Non BP
Finance | Enterprise Risk and Compliance | US | 24J | Compliance Management with SAP Global Trade Services | Non BP
Finance | Enterprise Risk and Compliance | US | 2OH | Continuous Control Monitoring with SAP Process Control | Non BP
Finance | Enterprise Risk and Compliance | US | 2U1 | Customs Management with SAP Global Trade Services | Non BP
Finance | Enterprise Risk and Compliance | US | 1WC | Embargo Control | Non BP
Finance | Enterprise Risk and Compliance | US | 3KY | Financial Operation Monitoring with SAP Financial Compliance | Non BP
Finance | Enterprise Risk and Compliance | US | BDT | Intrastat Processing | Non BP
Finance | Enterprise Risk and Compliance | US | 2U2 | Key Risk Indicator Monitoring with SAP Risk Management | Non BP
Finance | Enterprise Risk and Compliance | US | 1W8 | Legal Control | Non BP
Finance | Enterprise Risk and Compliance | US | 3JX | Preference Management with SAP Global Trade Services | Non BP
Finance | Enterprise Risk and Compliance | US | 3KX | Privacy Risk Detection with SAP Privacy Governance | Non BP
Finance | Enterprise Risk and Compliance | US | 1WE | Restricted Party Screening with SAP Watch List Screening | Non BP
Finance | Enterprise Risk and Compliance | US | 6NL | Security Risk Detection with SAP Privacy Governance | Non BP
Finance | Enterprise Risk and Compliance | US | 24H | Transfer of Bill of Materials for SAP Global Trade Services | Non BP
Finance | Enterprise Risk and Compliance | US | 24F | Transfer of Contact Person for SAP Global Trade Services | Non BP
Finance | Enterprise Risk and Compliance | US | 1WA | Transfer of Primary Master Data for SAP Global Trade Services | Non BP
Finance | Environmental Footprint Management | US | 5IM | Product Footprint Management | Non BP
Finance | Financial Operations | US | J60 | Accounts Payable | Non BP | 10 | 3 | 3 | 3 | 3 | 22
Finance | Financial Operations | US | J59 | Accounts Receivable | Non BP | 10 | 3 | 3 | 3 | 3 | 22
Finance | Financial Operations | US | 4X8 | Advanced Bank Statement Automation | Non BP
Finance | Financial Operations | US | 1WQ | Bill of Exchange | Non BP
Finance | Financial Operations | US | 1MV | Cash Application Integration | Non BP
Finance | Financial Operations | US | 2UV | Combined Invoice – Goods and Service Items | Non BP
Finance | Financial Operations | US | 2UT | Complementary Invoice – Pricing | Non BP
Finance | Financial Operations | US | 1S0 | Customer Payments | Non BP
Finance | Financial Operations | US | 2UW | Delivery of Goods on Behalf of Another Company | Non BP
Finance | Financial Operations | US | 1S2 | Digital Payments | Non BP
Finance | Financial Operations | US | 19M | Direct Debit | Non BP | 5 | 2 |  | 2 | 1 | 10
Finance | Financial Operations | US | 2RP | Electronic Documents | Non BP
Finance | Financial Operations | US | 43D | Integration with External Tax Calculation Engines | Non BP
Finance | Financial Operations | US | 1J5 | Invoice, Taxes and Complementary Postings | Non BP
Finance | Financial Operations | US | 1JT | Lockbox | Non BP | 3 | 2 |  | 2 | 1 | 8 | Standard BAI2 File
Finance | Financial Operations | US | 2PD | Provisioning of Overdue Receivables | Non BP | 5 | 2 |  | 2 | 1 | 10
Finance | Financial Operations | US | 55I | Royalties Settlement for Sales | Non BP
Finance | Financial Operations | US | 2JB | SAP Fiori Analytical Apps for Financial Accounting | Non BP | 1 | 3 |  | 2 | 1 | 7
Finance | Financial Operations | US | 4AV | Supplier Financing | Non BP
Finance | Real Estate Management | US | 5VX | Enable for Use and Contract Management | Non BP
Finance | Real Estate Management | US | 5YU | Enable for Use and Contract Management - Group Ledger IFRS | Non BP
Finance | Real Estate Management | US | 6EG | Enable for Use and Contract Management - Group Ledger IFRS (UPA) | Non BP
Finance | Real Estate Management | US | 6EF | Enable for Use and Contract Management (UPA) | Non BP
Finance | Real Estate Management | US | 5VY | External Occupancy and Contract Management | Non BP
Finance | Real Estate Management | US | 5YV | External Occupancy and Contract Management - Group Ledger IFRS | Non BP
Finance | Real Estate Management | US | 5W0 | Intercompany Occupancy and Contract Management | Non BP
Finance | Real Estate Management | US | 5YW | Intercompany Occupancy and Contract Management - Group Ledger IFRS | Non BP
Finance | Real Estate Management | US | 5VZ | Internal Occupancy and Cost Allocation | Non BP
Finance | Subscription Billing and Revenue Management | US | 47I | Contract Accounting - Cash Application | Non BP
Finance | Subscription Billing and Revenue Management | US | 2DP | Contract Accounting - Company Initiated Payments | Non BP
Finance | Subscription Billing and Revenue Management | US | 3L3 | Contract Accounting - Contract-Based Revenue Recognition | Non BP
Finance | Subscription Billing and Revenue Management | US | 2BI | Contract Accounting - Customer Initiated Payments | Non BP
Finance | Subscription Billing and Revenue Management | US | 2BK | Contract Accounting - Daily and Monthly Closing | Non BP
Finance | Subscription Billing and Revenue Management | US | 2SJ | Contract Accounting - External Tax Audit and Compliance Reporting | Non BP
Finance | Subscription Billing and Revenue Management | US | 33X | Contract Accounting - Group Ledger IFRS | Non BP
Finance | Subscription Billing and Revenue Management | US | 43Y | Contract Accounting - Integration with Sales Documents | Non BP
Finance | Subscription Billing and Revenue Management | US | 6WB | Contract Accounting – Intelligent Collections | Non BP
Finance | Subscription Billing and Revenue Management | US | 2AR | Contract Accounting - Master Data and Basic Functions | Non BP
Finance | Subscription Billing and Revenue Management | US | 2UJ | Contract Accounting - Open Item Management | Non BP
Finance | Subscription Billing and Revenue Management | US | 6WD | Convergent Invoicing - Cost Handling for Subscriptions and Usage | Non BP
Finance | Subscription Billing and Revenue Management | US | 6WC | Convergent Invoicing - Intercompany Settlement | Non BP
Finance | Subscription Billing and Revenue Management | US | 2KH | SAP Fiori Analytical Apps for Contract Accounting Manager | Non BP
Finance | Subscription Billing and Revenue Management | US | 5IK | Subscription Management with Convergent Invoicing | Non BP
Finance | Treasury Management | US | J77 | Advanced Bank Account Management | Non BP | 10 | 2 |  | 2 | 1 | 15
Finance | Treasury Management | US | J78 | Advanced Cash Operations | Non BP | 40 | 10 | 5 | 5 | 2 | 62
Finance | Treasury Management | US | 4MT | Advanced Payment Management | Non BP
Finance | Treasury Management | US | 6B5 | Asset-Backed Securities Management | Non BP
Finance | Treasury Management | US | 6B6 | Asset-Backed Securities Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 2O0 | Bank Fee Management | Non BP
Finance | Treasury Management | US | 2NZ | Bank Guarantee Management | Non BP
Finance | Treasury Management | US | 2O2 | Bank Guarantee Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 1EG | Bank Integration with File Interface | Non BP | 5 | 2 |  | 2 | 1 | 10 | Standard payment file formats with one House bank with 1 payment file type
Finance | Treasury Management | US | 16R | Bank Integration with SAP Multi-Bank Connectivity | Non BP
Finance | Treasury Management | US | BFA | Basic Bank Account Management | Non BP | 10 | 2 |  | 2 | 1 | 15
Finance | Treasury Management | US | BFB | Basic Cash Operations | Non BP | 10 | 2 |  | 2 | 1 | 15
Finance | Treasury Management | US | 3WY | Bond Management | Non BP
Finance | Treasury Management | US | 3WZ | Bond Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 1WV | Debt and Investment Management | Non BP
Finance | Treasury Management | US | 1X7 | Debt and Investment Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 1X1 | Foreign Currency Risk Management | Non BP
Finance | Treasury Management | US | 1X9 | Foreign Currency Risk Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 1XD | Hedge Accounting for FX Forward - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 3X1 | Hedge Accounting for FX Forward - Local GAAP | Non BP
Finance | Treasury Management | US | 2RW | Hedge Accounting for FX Option - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 3X2 | Hedge Accounting for FX Option - Local GAAP | Non BP
Finance | Treasury Management | US | 2UF | Hedge Accounting for FX Swap - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 6BP | In-House Banking | Non BP
Finance | Treasury Management | US | 2OI | Intercompany Debt and Investment Mgmt - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 2HU | Intercompany Foreign Exchange - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 2F2 | Intercompany Foreign Exchange Management | Non BP
Finance | Treasury Management | US | 1YI | Intercompany Process for Debt and Investment Mgmt | Non BP
Finance | Treasury Management | US | 1X3 | Interest Rate Derivatives Management | Non BP
Finance | Treasury Management | US | 1XB | Interest Rate Derivatives Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 49D | Letter of Credit Management | Non BP
Finance | Treasury Management | US | 49E | Letter of Credit Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 3L5 | Liquidity Planning | Non BP
Finance | Treasury Management | US | 1XN | Market Rates Management - Manually via Upload | Non BP
Finance | Treasury Management | US | 2UN | Money Market Mutual Fund Management | Non BP
Finance | Treasury Management | US | 2UO | Money Market Mutual Fund Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 1MN | SAP Fiori Analytical Apps for Treasury and Risk Management | Non BP
Finance | Treasury Management | US | 6ND | Securities Option Management | Non BP
Finance | Treasury Management | US | 6NE | Securities Option Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 5WF | Shareholding Management | Non BP
Finance | Treasury Management | US | 5WG | Shareholding Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 5OD | Stock Management | Non BP
Finance | Treasury Management | US | 5OE | Stock Management - Group Ledger IFRS | Non BP
Finance | Treasury Management | US | 34P | Treasury Workstation Cash Integration | Non BP
Human Resources | Core HR and Time Recording | US | 1FD | Employee Integration - SAP S/4HANA Enablement | Non BP
IT Management | Administration and Usability | US | 1LQ | Output Management | Non BP
Manufacturing | Manufacturing Operations | US | 2QW | Analytics for Production Unit - Plan/Actual Production Cost | Non BP | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
Manufacturing | Manufacturing Operations | US | 4R8 | Engineer-to-Order Production with Variant Configuration | Non BP | 2 | 5 | 5 | 1 | 1 | 14
Manufacturing | Manufacturing Operations | US | 3UK | Inbound Storage Tank Management - Process Manufacturing | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | BJE | Make-to-Order Production - Finished Goods Sales and Final Assembly | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 3OK | Make-to-Order Production - Process Manufacturing | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 1BM | Make-to-Order Production - Semifinished Goods Planning and Assembly | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 4OC | Make-to-Order Production for Sales Kits with Variant Configuration | Non BP | 2 | 5 | 5 | 1 | 1 | 14
Manufacturing | Manufacturing Operations | US | 1YT | Make-to-Order Production with Variant Configuration | Non BP | 2 | 5 | 5 | 1 | 1 | 14
Manufacturing | Manufacturing Operations | US | BJ8 | Make-to-Stock - Process Manufacturing Based on Process Order | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 2UG | Make-to-Stock - Process Manufacturing Based on Production Order | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | BJ5 | Make-to-Stock Production - Discrete Manufacturing | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 21D | Make-to-Stock Production with Variant Configuration | Non BP | 2 | 5 | 5 | 1 | 1 | 14
Manufacturing | Manufacturing Operations | US | 3L7 | Make-to-Stock with Co- and By-Products - Process Manufacturing | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 3UL | Make-to-Stock with Silo Material - Process Manufacturing | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 20N | Predictive Analytics Model Training - Supply Chain | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 1Y5 | Production Operations with Manufacturing Execution System | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Operations | US | 2JN | Production Operations with SAP Manufacturing Execution | Non BP | 2 | 5 | 5 | 1 | 1 | 14
Manufacturing | Manufacturing Operations | US | BJK | Production Subcontracting - External Processing | Non BP | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5
Manufacturing | Manufacturing Operations | US | BJN | Rework Processing - Stock-Manufactured Material | Non BP | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5
Manufacturing | Manufacturing Operations | US | BJQ | Rework Processing - Work-in-Process | Non BP | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5
Manufacturing | Manufacturing Operations | US | 42N | Tank Trailer Filling with Residuals | Non BP | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5
Manufacturing | Manufacturing Options | US | 2EM | Just-In-Time Supply to Customer | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | 53X | Just-In-Time Supply to Customer with Delivery Confirmation | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | BJH | Make-to-Stock Production - Repetitive Manufacturing | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | 1E3 | Material Replenishment with Kanban - External Procurement | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | 4B3 | Material Replenishment with Kanban - In-House Production | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | 4B4 | Material Replenishment with Kanban - Stock Transfer | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | BMY | Subcontracting | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Manufacturing Options | US | 5I2 | Subcontracting with SAP Business Network | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Production Engineering | US | 3LO | Change Manufacturing Bill of Material for Production | Non BP | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
Manufacturing | Production Engineering | US | 3LP | Mass Change Manufacturing Bill of Material for Production | Non BP | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
Manufacturing | Production Planning | US | 1Y2 | Demand-Driven Buffer Level Management | Non BP | 1 | 4 | 4 | 0.5 | 0.5 | 10
Manufacturing | Production Planning | US | 2QI | Demand-Driven Replenishment Planning and Execution | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Production Planning | US | J44 | Material Requirements Planning | Non BP | 1 | 4 | 4 | 1 | 1 | 11
Manufacturing | Production Planning | US | 65D | MRP Change Request Integration with SAP Business Network | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Production Planning | US | 4B5 | Predictive Material and Resource Planning | Non BP | 1 | 3 | 3 | 0.5 | 0.5 | 8
Manufacturing | Production Planning | US | 31L | Production Capacity Evaluation | Non BP | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5
Manufacturing | Production Planning | US | 3LQ | Production Capacity Leveling | Non BP | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5
Manufacturing | Quality Management | US | 2QN | Nonconformance Management | Non BP | 0.5 | 1 | 1 | 0.5 | 0.5 | 3.5
Manufacturing | Quality Management | US | 2F9 | Quality Management for Complaints Against Suppliers | Non BP | 0.5 | 1 | 1 | 0.5 | 0.5 | 3.5
Manufacturing | Quality Management | US | 2FA | Quality Management for Complaints from Customers | Non BP | 0.5 | 1 | 1 | 0.5 | 0.5 | 3.5
Manufacturing | Quality Management | US | 1E1 | Quality Management in Discrete Manufacturing | Non BP | 1 | 3 | 3 | 1 | 1 | 9
Manufacturing | Quality Management | US | 1FM | Quality Management in Procurement | Non BP | 1 | 3 | 3 | 1 | 1 | 9
Manufacturing | Quality Management | US | 1MP | Quality Management in Sales | Non BP | 1 | 3 | 3 | 1 | 1 | 9
Manufacturing | Quality Management | US | 1MR | Quality Management in Stock Handling | Non BP | 0.5 | 1 | 1 | 0.5 | 0.5 | 3.5
Manufacturing | Quality Management | US | 2QP | Quality Management of Internal Problems | Non BP | 0.5 | 1 | 1 | 0.5 | 0.5 | 3.5
Manufacturing | Quality Management | US | 2V0 | SAP Fiori Analytical Apps for Quality Management | Non BP | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
R&D/Engineering | Product Compliance | US | 3FC | Assess Dangerous Goods for a Product | Non BP
R&D/Engineering | Product Compliance | US | 31H | Assess Marketability of a Product | Non BP
R&D/Engineering | Product Compliance | US | 31G | Chemical Compliance Approval for Purchased Material and Supplier | Non BP
R&D/Engineering | Product Compliance | US | 31J | Chemical Compliance in the Value Chain | Non BP
R&D/Engineering | Product Compliance | US | 3G8 | Dangerous Goods in the Value Chain | Non BP
R&D/Engineering | Product Compliance | US | 6MT | Label Management | Non BP
R&D/Engineering | Product Compliance | US | 3VR | Manage Safety Data Sheets for Products | Non BP
R&D/Engineering | Product Compliance | US | 3VQ | Safety Data Sheets in the Value Chain | Non BP
R&D/Engineering | Product Compliance | US | 4OL | Substance Volume Tracking | Non BP
R&D/Engineering | Product Compliance | US | 5OJ | Supplier Compliance in the Value Chain | Non BP
R&D/Engineering | Product Engineering | US | 1NR | Engineering Bill of Material - Versions Management | Non BP
R&D/Engineering | Product Engineering | US | 22P | Manage Documents | Non BP
R&D/Engineering | Product Engineering | US | 2XU | Procurement of Materials with Variant Configuration | Non BP
R&D/Engineering | Product Engineering | US | 3ND | Product Structure Management | Non BP
R&D/Engineering | Product Engineering | US | 35Q | Product Structure Template Management | Non BP
R&D/Engineering | Product Engineering | US | 6W9 | Set Up Advanced Solution Bundle | Non BP
R&D/Engineering | Product Engineering | US | 22T | Set Up Configurable Model using Variant Configuration | Non BP
R&D/Engineering | Product Lifecycle Management | US | 22R | Advanced Ingredient Replacement for Recipes | Non BP
R&D/Engineering | Product Lifecycle Management | US | 64F | Bill of Material Management | Non BP
R&D/Engineering | Product Lifecycle Management | US | 6OT | Bill of Material Management Professional | Non BP
R&D/Engineering | Product Lifecycle Management | US | 2G6 | Embedded Software Management | Non BP
R&D/Engineering | Product Lifecycle Management | US | 1QC | Formulation - Recipe Development | Non BP
R&D/Engineering | Product Lifecycle Management | US | 2WK | Handover of Product Information to SAP Asset Intelligence Network | Non BP
R&D/Engineering | Product Lifecycle Management | US | 2YC | Intelligent Content Processing for Document Classification | Non BP
R&D/Engineering | Product Lifecycle Management | US | 5QC | Product Change Management with Change Records - Process Industries | Non BP
R&D/Engineering | Product Lifecycle Management | US | 64E | Product Change Mgmt with Change Records - Discrete Industries | Non BP
R&D/Engineering | Product Lifecycle Management | US | 1QG | Recipe Handover to Production - Bill of Material | Non BP
R&D/Engineering | Product Lifecycle Management | US | 2G5 | Software Compatibility Management | Non BP
R&D/Engineering | Product Lifecycle Management | US | 1QA | Specification Management for Recipes | Non BP
Sales | Order and Contract Management | US | 5D2 | Advanced Intercompany Sales | Non BP | 3 | 3 | 1 | 1 | 1 | 9
Sales | Order and Contract Management | US | 2QS | Analytics for Sales - Central Stock with Returns | Non BP | 0 | 1 | 0 | 1 | 0.5 | 2.5
Sales | Order and Contract Management | US | 4A1 | Automation of Order-to-Invoice with SAP Business Network | Non BP | 3 | 3 | 3 | 2 | 1 | 12 | This solution process is excluded from default activation (efforts from Ariba, basis, abap are required)
Sales | Order and Contract Management | US | 6JM | Basic Business Process Scheduling | Non BP | 1 | 0.5 | 1 | 0.5 | 0.5 | 3.5
Sales | Order and Contract Management | US | 4X9 | Create Sales Orders from Unstructured Data | Non BP | 1 | 1 | 0.5 | 1 | 0.5 | 4 | BTP consultant efforts are required
Sales | Order and Contract Management | US | 1EZ | Credit Memo Processing | Non BP | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | Technical efforts are required for workflow logic
Sales | Order and Contract Management | US | 1IU | Customer Consignment | Non BP | 3 | 3 | 2 | 3 | 1 | 12
Sales | Order and Contract Management | US | BKP | Customer Returns | Non BP | 2 | 2 | 1 | 1 | 1 | 7
Sales | Order and Contract Management | US | 3TE | Customer Returns for Non-Stock and Service Materials | Non BP | 2 | 2 | 1 | 1 | 1 | 7
Sales | Order and Contract Management | US | 5CX | Customer Returns for Sales Kits | Non BP | 2 | 2 | 1 | 1 | 1 | 7
Sales | Order and Contract Management | US | 1Z3 | Customer Returns with Direct Shipment from Customer to Supplier | Non BP | 2 | 2 | 1 | 1 | 1 | 7
Sales | Order and Contract Management | US | 1F1 | Debit Memo Processing | Non BP | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 3
Sales | Order and Contract Management | US | 1MI | Delivery Processing Without Order Reference | Non BP | 1 | 1 | 0.5 | 0.5 | 0.5 | 3.5
Sales | Order and Contract Management | US | 1Z1 | Digital Payments - Sales | Non BP | 5 | 6 | 4 | 3 | 1 | 19 | Technical efforts ffor integration with the payment hub for authorization when creating sales documents sales side 3 scenarios, integration of BP,SO with payment hub for authorization, reauthorization, verification, cancellation...
Sales | Order and Contract Management | US | 1Z6 | External Billing | Non BP | 2 | 3 | 2 | 1 | 1 | 9 | Technical efforts -use of the external billing interface to create billing documents
Sales | Order and Contract Management | US | BKA | Free Goods Processing | Non BP | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 3
Sales | Order and Contract Management | US | BDA | Free of Charge Delivery | Non BP | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 3
Sales | Order and Contract Management | US | 2EL | Integration of Sales with External Buyers | Non BP | 4 | 4 | 5 | 3 | 2 | 18 | Technical efforts are required for interfaces (APIs) to simplify and automate exchanging sales documents and their follow-on messages for below processes enable B2B integration with the corresponding Integration of SAP S/4HANA Cloud Procurement with Suppliers (2EJ) scope item (Prerequisites-PO must have been created and automatically sent to the SAP S/4HANA system (supplier side) An Order Confirmation is automatically sent to the Buyer system An Order Confirmation Change is automatically sent to the Buyer system ASN is automatically sent to the Buyer system, Invoice is sent to the Buyer system.
Sales | Order and Contract Management | US | BKL | Invoice Correction Process with Credit Memo | Non BP | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
Sales | Order and Contract Management | US | BDQ | Invoice Correction Process with Debit Memo | Non BP | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
Sales | Order and Contract Management | US | BDD | Lean Customer Returns | Non BP | 2 | 1 | 1 | 1 | 1 | 1
Sales | Order and Contract Management | US | 1MC | Omnichannel Convergent Billing | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | BKN | Order-to-Cash Performance Monitoring | Non BP | 0.5 | 1 | 0 | 1 | 0.5 | 3
Sales | Order and Contract Management | US | 1O0 | Planning Apps for Sales | Non BP | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5
Sales | Order and Contract Management | US | 2YJ | Predictive Analytics Model Training - Sales | Non BP | 0.5 | 2 | 0 | 1 | 0.5 | 4
Sales | Order and Contract Management | US | BDW | Returnables Processing | Non BP | 1.5 | 1.5 | 1 | 1 | 1 | 6
Sales | Order and Contract Management | US | 2EQ | Sale of Services | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | 2TT | Sales Commissions - External Sales Representative | Non BP | 3 | 3 | 2 | 3 | 2 | 13
Sales | Order and Contract Management | US | I9I | Sales Contract Management | Non BP | 2 | 2 | 1 | 1 | 1 | 7 | quantity and value contract considered
Sales | Order and Contract Management | US | 1IQ | Sales Inquiry | Non BP | 1 | 1 | 0 | 0.5 | 0.5 | 3
Sales | Order and Contract Management | US | BDN | Sales of Non-Stock Item with Order-Specific Procurement | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | BDH | Sales Order Entry with One-Time Customer | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | BKK | Sales Order Fulfillment Monitoring and Operations | Non BP | 1 | 1 | 1 | 1 | 1 | 5 | 14 reports in this scope id
Sales | Order and Contract Management | US | BKX | Sales Order Processing - SEPA Direct Debit Handling | Non BP | [5 empty] | 0 | Not applicable for USA best practices
Sales | Order and Contract Management | US | 2ET | Sales Order Processing for Non-Stock Material | Non BP | 2 | 2 | 1 | 1 | 1 | 7
Sales | Order and Contract Management | US | 31Q | Sales Order Processing for Sales Kits | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | BKJ | Sales Order Processing with Customer Down Payment | Non BP | 1.5 | 2 | 1 | 1 | 1 | 6.5
Sales | Order and Contract Management | US | BKZ | Sales Order Processing with Invoice List and Collective Billing | Non BP | 1 | 1 | 1 | 1 | 1 | 5 | two scenarios included for invoice lists and collective invoicing
Sales | Order and Contract Management | US | BD3 | Sales Processing using Third-Party with Shipping Notification | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | 4R6 | Sales Processing using Third-Party with Variant Configuration | Non BP | 4 | 4 | 2 | 2 | 1 | 13 | This solution requires additional licenses
Sales | Order and Contract Management | US | BDK | Sales Processing Using Third-Party Without Shipping Notification | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | BDG | Sales Quotation | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sales | Order and Contract Management | US | 1B6 | Sales Rebate Processing | Non BP | 3 | 3 | 2 | 1 | 1 | 10 | sales rebates with one customer
Sales | Order and Contract Management | US | 4LZ | Sales Scheduling Agreement with Consignment | Non BP | 4 | 4 | 3 | 2 | 1 | 14 | integration with buyer system for storing purchase order info in sales order-efforts of ABAP and basis are required. EDI are required for ASN,Invoice and credit memo
Sales | Order and Contract Management | US | 3NR | Sales Scheduling Agreements | Non BP | 3 | 3 | 3 | 2 | 1 | 12 | integration with buyer system for storing purchase order info in sales order-efforts of ABAP and basis are required. EDI are required for ASN,Invoice also includes configuration of set up guide (38 pages)
Sales | Order and Contract Management | US | 6KO | SAP Customer Experience Entities with SAP Service and Sales Cloud | Non BP | 2 | 3 | 3 | 1 | 1 | 10 | Basis and ABAP efforts are required as per setup guide to integration between SAP S/4HANA and SAP Sales Cloud and SAP Service Cloud Version 2 using SAP Cloud Integration related to business partners, company code, sales organization, materials, funcional location, equipment, sales quote
Sales | Order and Contract Management | US | 1BS | SAP Fiori Analytical Apps for Sales | Non BP | 1 | 3 | 1 | 2 | 1 | 8 | 16 reports considered in scope
Sales | Order and Contract Management | US | 4H2 | Self-Billing | Non BP | 2 | 3 | 4 | 3 | 1 | 13 | This solution process is excluded from default activation integrate SAP S/4HANA system with SAP Self-Billing Cockpit. SAP Self-Billing Cockpit is licensed in the SAP Store. efforts required from basis, abap efforts from sales side is given considering sell from stock scenario and integration testing efforts
Sales | Order and Contract Management | US | BD9 | Sell from Stock | Non BP | 2 | 2 | 1 | 1 | 1 | 7
Sales | Order and Contract Management | US | 5MQ | Sell from Stock with Valuated Stock in Transit | Non BP | 1.5 | 1.5 | 1 | 1 | 1 | 6
Sales | Order and Contract Management | US | 57Z | Subscription Management with Sales Billing | Non BP | 2 | 2 | 2 | 2 | 1 | 9 | ABAP and basis efforts required for integratiing SAP Subscription billing with S/4HANA for billing
Sales | Sales Force Support | US | 41V | Presales Management | Non BP | [6 empty] | This is not in scope ofbest practices 2302 SP02, Prviate Cloud
Sales | Solution Business Management | US | 4Q5 | Solution Quotation | Non BP | 2 | 2 | 2 | 1 | 1 | 8 | prerequisite- Service Order Management, Service Contract Management must be implemented
Service | Service Master Data & Agreement Management | US | 6AU | Service with Advanced Execution | Best Practice | 3 | 2 | 2 | 2 | 1 | 10
Service | Service Master Data & Agreement Management | US | 6F1 | Recurring Services with Advanced Execution | Best Practice | 2 | 3 | 2 | 2 | 1 | 10
Service | Service Master Data & Agreement Management | US | 426 | Service Contract Management | Best Practice | 2 | 2 | 1 | 2 | 1 | 8
Service | Service Master Data & Agreement Management | US | 43B | Service Monitoring and Analytics | Best Practice | 3 | 2 | 2 | 1 | 1 | 9
Service | Service Master Data & Agreement Management | US | 63Y | Warranty Claim Management - Customer Claim Processing | Best Practice | 3 | 2 | 2 | 2 | 1 | 10
Service | Service Master Data & Agreement Management | US | 5HR | Warranty Claim Management - Supplier Recovery Processing | Best Practice | 4 | 3 | 2 | 2 | 2 | 13
Service | Service Operations & Processes | US | 3XK | In-House Repair | Best Practice | 4 | 3 | 2 | 2 | 2 | 13
Service | Service Operations & Processes | US | 41W | Interaction Center Service Request Management | Best Practice | 2 | 2 | 1 | 2 | 1 | 8
Service | Service Operations & Processes | US | 4X5 | Recurring Services | Best Practice | 2 | 2 | 1 | 2 | 1 | 8
Service | Service Operations & Processes | US | 41Z | Service Order Management | Best Practice | 3 | 2 | 1 | 2 | 1 | 9
Solutions for Specific Industries | Automotive | US | 5ON | Digital Vehicle | Non BP
Solutions for Specific Industries | Oil and Gas | US | 6VA | Field Logistics Analytics | Non BP
Solutions for Specific Industries | Oil and Gas | US | 40G | Field Logistics Planning and Execution | Non BP
Solutions for Specific Industries | Oil and Gas | US | 6BA | Field Logistics Planning and Execution - Containers and Voyages | Non BP
Solutions for Specific Industries | Oil and Gas | US | 5OM | Field Logistics Planning and Execution – Direct Procurement | Non BP
Solutions for Specific Industries | Oil and Gas | US | 4AH | Field Logistics Planning and Execution – Supplier Items | Non BP
Sourcing and Procurement | Central Procurement | US | 4QN | Central Procurement with SAP Ariba Sourcing | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 2ME | Central Purchase Contracts | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 2XT | Central Purchasing | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 1XI | Central Requisitioning | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 4B0 | Contract for Central Procurement with SAP Ariba Contracts | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Additional license & Integration effort needed
Sourcing and Procurement | Central Procurement | US | 4RD | Direct Material Sourcing | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Additional license & Integration effort needed
Sourcing and Procurement | Invoice Management | US | 1L2 | Supplier Quote automation with SAP Ariba Commerce Automation | Non BP | [5 empty] | 0 | This is not existing in best practices 2302 SP02, Private Cloud
Sourcing and Procurement | Invoice Management | US | J82 | Automated Purchase-to-Pay with SAP Ariba Commerce Automation | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Additional license & Integration effort needed
Sourcing and Procurement | Invoice Management | US | 2TW | Complementary Procurement Functions | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Invoice Management | US | BNX | Consumable Purchasing | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Technical effort for Workflow is required
Sourcing and Procurement | Invoice Management | US | 2TX | Direct Procurement with Inbound Delivery | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Invoice Management | US | 22K | External Workforce Procurement via SAP Fieldglass | Non BP | 2 | 2 | 2 | 1 | 1 | 8 | Additional license & Integration effort needed
Sourcing and Procurement | Invoice Management | US | 4N6 | Invoice Processing with SAP Central Invoice Management | Non BP | [5 empty] | 0 | This is not existing in best practices 2302 SP02, Private Cloud
Sourcing and Procurement | Invoice Management | US | J45 | Procurement of Direct Materials | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Technical effort for Workflow is required
Sourcing and Procurement | Invoice Management | US | 22Z | Procurement of Services | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Technical effort for Workflow is required
Sourcing and Procurement | Invoice Management | US | 18J | Requisitioning | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Technical effort for Workflow is required
Sourcing and Procurement | Invoice Management | US | 2UU | Returnable Packaging to Vendor | Non BP | [5 empty] | 0
Sourcing and Procurement | Invoice Management | US | 4R2 | Service Procurement with SAP Business Network and SAP Fieldglass | Non BP | 2 | 1 | 2 | 1 | 1 | 7 | Additional license & Integration effort needed
Sourcing and Procurement | Invoice Management | US | 2LG | Supplier Consignment | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Operational Procurement | US | 5JT | Automation of Central Procurement Quote with SAP Business Network | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Additional license & Integration effort needed
Sourcing and Procurement | Operational Procurement | US | 42K | Automation of Source-to-Pay with SAP Business Network | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Additional license & Integration effort needed
Sourcing and Procurement | Operational Procurement | US | BLF | Batch Management | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | Batch integration required from PP and SD
Sourcing and Procurement | Operational Procurement | US | 2NV | Guided Buying Capability with SAP Ariba Buying | Non BP | 2 | 1 | 2 | 1 | 1 | 7 | Additional license & Integration effort needed
Sourcing and Procurement | Operational Procurement | US | 3EN | Guided Buying for Central Procurement with SAP Ariba Buying | Non BP | 2 | 1 | 2 | 1 | 1 | 7 | Additional license & Integration effort needed
Sourcing and Procurement | Operational Procurement | US | 2EJ | Integration of Procurement with External Suppliers | Non BP | [5 empty] | 0
Sourcing and Procurement | Operational Procurement | US | 1QR | Predictive Analytics for Purchase Contract Quantity Consumption | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Operational Procurement | US | 41F | Procurement of Pipeline Materials | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Operational Procurement | US | 2R7 | Purchasing Rebate Processing | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Operational Procurement | US | 2NY | Scheduling Agreement for Consignment Procurement | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Operational Procurement | US | 2NX | Scheduling Agreement for Subcontracting Procurement | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Operational Procurement | US | BMR | Scheduling Agreements in Procurement | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Operational Procurement | US | 2XW | Proposal of New Catalog Item | Non BP | [5 empty] | 0
Sourcing and Procurement | Operational Procurement | US | 30W | Proposal of Options for materials without purchase contract | Non BP | [5 empty] | 0
Sourcing and Procurement | Operational Procurement | US | BLL | Serial Number Management | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Procurement Analytics | US | 2QU | Analytics - Purchase Order Visibility and Procurement Spend | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Procurement Analytics | US | 1JI | Real-Time Reporting and Monitoring for Procurement | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Sourcing and Contract Management | US | 3ZF | Central Sourcing | Non BP | 2 | 1 | 2 | 1 | 1 | 7 | Additional license & Integration effort needed
Sourcing and Procurement | Sourcing and Contract Management | US | 4AZ | Contract Management with SAP Ariba Contracts | Non BP | 2 | 1 | 2 | 1 | 1 | 7 | Additional license & Integration effort needed
Sourcing and Procurement | Sourcing and Contract Management | US | 6AN | Contract Price Renegotiation | Non BP | 2 | 1 | 2 | 1 | 1 | 7 | Additional license & Integration effort needed
Sourcing and Procurement | Sourcing and Contract Management | US | 2OQ | Integration to SAP Enterprise Contract Assembly | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Sourcing and Contract Management | US | 4RI | Preferred Supplier List | Non BP | [5 empty] | 0
Sourcing and Procurement | Sourcing and Contract Management | US | 6AJ | Procurement Planning Integration with Product Sourcing | Non BP | [5 empty] | 0
Sourcing and Procurement | Sourcing and Contract Management | US | BMD | Purchase Contract | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Sourcing and Contract Management | US | 1XF | Request for Price | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Sourcing and Contract Management | US | 1XV | SAP S/4HANA for Enterprise Contract Management | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Sourcing and Contract Management | US | 4BL | Sourcing with SAP Ariba Sourcing | Non BP | 2 | 1 | 2 | 1 | 1 | 7 | Additional license & Integration effort needed
Sourcing and Procurement | Supplier Management | US | 19C | Activity Management in Procurement | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Supplier Management | US | 3FY | Prediction of Delivery Date for Purchase Order Items | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Sourcing and Procurement | Supplier Management | US | 19E | Supplier Classification and Segmentation | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Supplier Management | US | SL4 | Supplier Evaluation and Performance Monitoring | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Sourcing and Procurement | Product Engineering | US | 43E | Intelligent Approval Workflow | Non BP | [5 empty] | 0 | This is not existing in best practices 2302 SP02, Private Cloud
Sourcing and Procurement | Product Engineering | US | 2XU | Procurement of Materials with Variant Configuration | Non BP | 2 | 1 | 2 | 1 | 1 | 7 | Integration with SD and PP
Supply Chain | Advanced Order Promising | US | 1JW | Advanced Available-to-Promise Processing | Non BP | 2 | 1 | 2 | 1 | 1 | 7 | This solution requires additional license
Supply Chain | Advanced Order Promising | US | 6JM | Basic Business Process Scheduling | Non BP | 1 | 1 | 0 | 1 | 0.5 | 3.5
Supply Chain | Advanced Transportation | US | 4OZ | Planning of External Transportation Requirements | Non BP | 2 | 1 | 2 | 1 | 1 | 7
Supply Chain | Advanced Warehousing | US | 1VD | Advanced Warehouse Outbound Processing to Customer | Non BP | 2 | 1 | 1 | 1 | 1 | 6 | This solution requires additional license
Supply Chain | Inventory | US | BMC | Core Inventory Management | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Inventory | US | 4LO | Enablement of SAP Excise Tax Management | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Inventory | US | 4LU | Physical Inventory - Cycle Counting | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Inventory | US | BML | Physical Inventory - Inventory Count and Adjustment | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Inventory | US | BMK | Return to Supplier | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Logistics Cross Topics | US | 4MM | Handling Unit Management | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Order Promising | US | 6LJ | Available-to-Promise Processing | Non BP | 1 | 1 | 0.5 | 1 | 0.5 | 4
Supply Chain | Warehousing | US | 1FS | Basic Warehouse Inbound Processing from Supplier | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | 1V9 | Basic Warehouse Inbound Processing from Supplier with Quality Management | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | 1G2 | Basic Warehouse Outbound Processing to Customer | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | 4RQ | Decentralized EWM - Ad Hoc Goods Issue | Non BP | 3 | 1 | 2 | 1 | 1 | 8 | Additional setup required
Supply Chain | Warehousing | US | 4RO | Decentralized EWM - Inbound Processing | Non BP | 3 | 1 | 2 | 1 | 1 | 8 | Additional setup required
Supply Chain | Warehousing | US | 4RP | Decentralized EWM - Outbound Processing | Non BP | 3 | 1 | 2 | 1 | 1 | 8 | Additional setup required
Supply Chain | Warehousing | US | 4RR | Decentralized EWM - Physical Inventory | Non BP | 3 | 1 | 2 | 1 | 1 | 8 | Additional setup required
Supply Chain | Warehousing | US | 4RS | Decentralized EWM - Replenishment | Non BP | 3 | 1 | 2 | 1 | 1 | 8 | Additional setup required
Supply Chain | Warehousing | US | 4UA | Decentralized EWM - Technical Integration ERP | Non BP | 3 | 1 | 2 | 1 | 1 | 8 | Additional setup required
Supply Chain | Warehousing | US | 1FU | Initial Stock Upload for Warehouse | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Warehousing | US | 1FW | Physical Inventory in Warehouse | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | 1VB | Production Integration - Component Consumption and Receipt in Warehouse | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | 1FY | Replenishment in Warehouse | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | BGG | SAP Fiori Analytical Apps for Inventory and Warehouse Management | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Warehousing | US | 1G0 | Scrapping in Warehouse | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Warehousing | US | 1V5 | Warehouse Inbound Processing from Supplier with Batch Management | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | 1V7 | Warehouse Outbound Processing to Customer with Batch Management | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Quality Management | US | 1MR | Quality Management in Stock Handling | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Warehousing | US | 2LN | Basic Avalibale to promise processing | Non BP | 1 | 1 | 1 | 1 | 1 | 5
Supply Chain | Quality Management | US | 2FA | Quality Management for Complaints from Customers | Non BP | 2 | 1 | 1 | 1 | 1 | 6
Supply Chain | Inventory | US | 2UU | Returnable Packaging | Non BP | [5 empty] | 0